## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Mahula ( 315354 ) of Char Mahula under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur | SM/09739 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at MAHULA G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000517/2021-2022 | 349/BSD | 27/08/2021 | 26/09/2021 | IMAGIN COMMUNICATION | 4.16 | 4.16 | 100 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Mahula ( 315354 ) of Char Mahula under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur | SM/09739 | Retrofitting | Laying of 160mm dia UPVC pipeline and road restoration work for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Char Mahula (village code 315354) under Char Mahula Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/000153/2022-2023 | 148/BSD | 12/04/2022 | 12/05/2022 | SANJIB GHOSH | 4.84 | 4.84 | 99.95 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Mahula ( 315354 ) of Char Mahula under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur | SM/09739 | Retrofitting | Laying of 110mm dia UPVC pipeline in connection providing Functional Household Tap Connection FHTC in connection with JJM and Jal Swapna under command area of village of Char Mahula Village code 315354 under Char Mahula W/S Scheme in the dist of MSD PHE DTE. Tender no - 182 of 21-22 by AE BSD |  |  | VCH/000004/2022-2023 | 03-MSD/22-23 | 14/04/2022 | 14/04/2022 | S. DUTTA | 4.81 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Mahula ( 315354 ) of Char Mahula under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur | SM/09739 | Retrofitting | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Char Mahula (village code 315354) under Char Mahula Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/001730/2021-2022 | 91/BSD | 07/03/2022 | 22/03/2022 | S. DUTTA | 4.81 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Mahula ( 315354 ) of Char Mahula under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur | SM/09739 | Retrofitting | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Beldanga-I & II Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/001641/2021-2022 | 480/MURD | 22/02/2022 | 23/04/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 47.33 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Mahula ( 315354 ) of Char Mahula under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur | SM/09739 | Retrofitting | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Berhampore Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-B |  | JUNIOR ENGINEER 1,JUNIOR ENGINEER_BERHAMPORE BLOCK | ORD/001671/2021-2022 | 298/MURD | 03/02/2022 | 04/04/2022 | ENVIROTECH SOLUTIONS | 32.69 | 0 | 0 | 1
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Mahula ( 315354 ) of Char Mahula under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur | SM/09739 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Charmahula ( Village Code-315354) under Charmahula Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. (Scheme I.D.-0001723196) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001466/2021-2022 | 279/MURD | 03/02/2022 | 04/04/2026 | MAA CONSTRUCTION | 42.13 | 41.13 | 97.64 | 100
Total | [13 empty] | 140.76 | 50.14 | 35.62