## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Surangapur (315540) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad | SM/09741 | Retrofitting | Providing Functional Household Tap Connections ( 50 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Surangapur ( Village Code -315540) under Surangapur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000108/2024-2025 | 2210/MURD | 02/08/2024 | 01/12/2025 | SARKAR WATER SUPPLY AGENCY | 2.58 | 0 | 0 | 100
Total | [13 empty] | 2.58 | 0 | 0