## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jaladipur ( 313860 ) of Basudebpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under Murshi | SM/09744 | Retrofitting | Laying of balance work of HDPE pipe Risingmain of Basudebpur Water Supply Scheme under Jangipur Sub Division,P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000617/2020-2021 | 654/MURD | 18/02/2021 | 19/04/2021 | JOY BISHNU ENGINEERING CO. | 7.91 | 7.83 | 99.04 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jaladipur ( 313860 ) of Basudebpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under Murshi | SM/09744 | Retrofitting | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL- 15 |  |  | VCH/000862/2022-2023 | 370-MSD/22-23 | 21/10/2022 | 21/10/2022 | EASTERN RAILWAY (MALDA DIVISION) | 20.99 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jaladipur ( 313860 ) of Basudebpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under Murshi | SM/09744 | Retrofitting | Providing Functional Household Tap Connections (FHTC) (1974 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Jaladipur ( Village Code -313860) under Basudebpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000639/2023-2024 | 3440/MURD | 03/11/2023 | 02/01/2024 | BHOWMIK CONSTRUCTION | 67.6 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jaladipur ( 313860 ) of Basudebpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under Murshi | SM/09744 | Retrofitting | Preparation of design, Drawing and approval from the N.H.A.I Authorities including supply of 200 mm dia 8 mm thick MS Water Carring Pipe, 600 mm dia 10 mm thick MS casing Pipe & Pushing of casing pipe by Hydraulic Jacking Technique Method across the Chainage 270+550 of the N.H.-34 of at Mouza-Basudebpur of Basudebpur adjoining mouza W/S Scheme & across at chainage 273+100 of the N.H.-34 of at Mouza-Joykrishnapur of Joykrishnapur W/S Scheme in Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000853/2022-2023 | 755/MURD | 16/03/2023 | 14/06/2023 | SAMBHU NATH ROY | 62.1 | 26.03 | 41.92 | 0
Total | [13 empty] | 158.59 | 33.86 | 21.35