## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bara Jumla (314144) Krishna Sail (314143) of Putia & adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II | SM/09746 | Retrofitting | Cleaning & Washing of pipe line at Village Bara Jumla (Village Code-314144) & Krishna Sail (Village Code- 314143) in cinnection with FHTC work under Putia Water Supply Scheme) | ASSISTANT ENGINEER |  | ORD/000315/2022-2023 | 259/JSD | 01/06/2022 | 01/07/2022 | BISWAS CONSTRUCTION PAN NO : AHNPB6929M | 4.02 | 4.04 | 100.31 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bara Jumla (314144) Krishna Sail (314143) of Putia & adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II | SM/09746 | Retrofitting | Laying pipe line at village Bara Jumla (Village Code- 314144) & Krishnaa Sail (Village Code-314143) in connection with FHTC work under Putia Water Supply Scheme under Jangipur Sub-Division under Murshidabad Division, P.H.Engineering Dte.https://app2.wbphed.gov.in/phed_v3/FAF00242/openDetail01new.html | ASSISTANT ENGINEER |  | ORD/000338/2022-2023 | 274/JSD | 01/06/2022 | 01/07/2022 | BISWAS CONSTRUCTION PAN NO : AHNPB6929M | 3.85 | 3.85 | 99.86 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bara Jumla (314144) Krishna Sail (314143) of Putia & adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II | SM/09746 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000004/2022-2023 | 889/D/MURD | 05/04/2022 | 05/04/2022 | Resource Division | 30.5 | 0 | 0 | 0
Total | [13 empty] | 38.38 | 7.88 | 20.54