## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Popara ( 314326 ) of Sagardighi Zone - II under Ground Water Based Water Supply Scheme for arsenic affected areas of Sagardighi Block of Murshidabad District under M | SM/09748 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) of mouza Bara Jumla (Village Code-314144, Krishnaa Sail(Village Code-314143) of Putia and ajoining moujas under Ground water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj II Block & mouza Joykrishnapur (Village Code-313880), of Joykrishnapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block, and mouza Popara (Village Code-314326) of Sagardighi Zone-II Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0005019109), 0001723441 & 0005184147) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 2 | ORD/001601/2021-2022 | 341/MURD | 10/02/2022 | 02/06/2026 | CHAKRABORTY CONSTRUCTION | 416 | 0 | 0 | 12
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Popara ( 314326 ) of Sagardighi Zone - II under Ground Water Based Water Supply Scheme for arsenic affected areas of Sagardighi Block of Murshidabad District under M | SM/09748 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 889/E/MURD | 05/04/2022 | 05/04/2022 | Resource Division | 15.53 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Popara ( 314326 ) of Sagardighi Zone - II under Ground Water Based Water Supply Scheme for arsenic affected areas of Sagardighi Block of Murshidabad District under M | SM/09748 | Retrofitting | Providing Functional Household Tap Connections (FHTC) (1250 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Popara under Sagardighi Zone-II Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000648/2023-2024 | 3713/MURD | 05/12/2023 | 03/02/2024 | SANDIP KUMAR BISWAS | 44.69 | 0 | 0 | 0
Total | [13 empty] | 476.22 | 0 | 0