## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khanpur (313989) of Prasadpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District under Murshidabad | SM/09757 | Retrofitting | Renovation of U.P.V.C of pipe line from Shib Mandir to Kartik Mandir due to widening of Bituminous Road of Prosadpur Water Supply Scheme under Jangipur Sub Division,P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000722/2020-2021 | 3328 / MURD | 31/12/2020 | 14/02/2021 | ARJU CONSTRUCTION | 4.99 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khanpur (313989) of Prasadpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District under Murshidabad | SM/09757 | Retrofitting | Renovation of UPVC pipe line from Dulal kali to Kartik Mandir due to widening of Bituminous Road of Prosadpur W/S Scheme in an emergency basis under Jangipur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/000723/2020-2021 | 79/JSD | 26/02/2021 | 28/03/2021 | T.R. CONSTRUCTION | 5 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khanpur (313989) of Prasadpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District under Murshidabad | SM/09757 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of Bamuha, Khidirpur, Khanpur (Nos FHTC-2996 Nos) (Village code-313962,313990,313989) under PRASADPUR Ground Water Based Water Supply Scheme of Suti-II Block and Kalinagar (FHTC-4077 Nos) (Village code-313899) under Raturi Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID-0005019110 & 0001723413) | ASSISTANT ENGINEER |  | ORD/001659/2021-2022 | 558/MURD | 28/02/2022 | 27/08/2022 | ALOK ENTERPRISE( A UNIT OF SAKET TREXIM PVT.LTD.) | 332.59 | 0 | 0 | 0
Total | [13 empty] | 342.59 | 0 | 0