## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kishorpur (313961) of Kishorpur and adjonining mouzas under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad Dis | SM/09760 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000003/2022-2023 | 889/C/MURD | 05/04/2022 | 05/04/2022 | Resource Division | 5.21 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kishorpur (313961) of Kishorpur and adjonining mouzas under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad Dis | SM/09760 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kishorpur (Village code 313961) under Kishorpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-II Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723400 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/001609/2021-2022 | 426/MURD | 17/02/2022 | 18/04/2022 | BISWAS CONSTRUCTION | 40.15 | 38.52 | 95.95 | 0
Total | [13 empty] | 45.36 | 38.52 | 84.93