## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di | SM/09763 | Retrofitting | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Edrakpur (village code 315547) under Edrakpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000073/2022-2023 | 178/BSD | 12/04/2022 | 27/04/2022 | M/S.S.S. ENTERPRISE | 4.83 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di | SM/09763 | Retrofitting | Laying of 90mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Edrakpur (village code 315547) under EdrakpurWater Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/000074/2022-2023 | 179/BSD | 12/04/2022 | 27/04/2022 | SWAPAN DAS | 4.83 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di | SM/09763 | Retrofitting | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Edrakpur (village code 315547) under Edrakpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000072/2022-2023 | 177/BSD | 12/04/2022 | 27/04/2022 | SOUVIK HALDER | 4.85 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di | SM/09763 | Retrofitting | LAYING OF 110 MM DIA UPVC PIPELINE FOR PROVIDING FHTC IN CONNECTION WITH JJM EDRAKPUR UNDER EDRAKPUR W/S SCHEME UNDER MSD. PHE DTE TENDER NO 222 OF 21-22 AE BSD |  |  | VCH/000316/2022-2023 | 177-MSD/22-23 | 17/05/2022 |  | M/S SS ENTERPRISE (SUKESH GHOSH) | 4.83 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di | SM/09763 | Retrofitting | Distribution system 110mm, 90mm and 75mm dia pipe in connection with FHTC of Edrakpur piped water supply scheme at Raghunathpur village of EDRAKPUR & its adjoining mouzas at Nowda Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/000139/2022-2023 | 187/BSD | 28/04/2022 | 28/05/2022 | RAFIKUL HASAN | 4.51 | 4.15 | 91.9 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di | SM/09763 | Retrofitting | Distribution system 110mm, 90mm and 75mm dia pipe in connection with FHTC of Edrakpur piped water supply scheme of Nawda village of EDRAKPUR & its adjoining mouzas at Nowda Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/000183/2022-2023 | 190/BSD | 28/04/2022 | 28/05/2022 | MOINAK CHATTOPADHYAY | 4.76 | 4.76 | 100.07 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di | SM/09763 | Retrofitting | Distribution system 110mm, 90mm and 75mm dia pipe in connection with FHTC of Edrakpur piped water supply scheme at Raghunathpur village of EDRAKPUR & its adjoining mouzas at Nowda Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/000140/2022-2023 | 189/BSD | 28/04/2022 | 28/05/2022 | RAFIKUL HASAN | 4.76 | 4.77 | 100.22 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di | SM/09763 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) of mouza Edrakpur (Village code 315547), of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block, of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID 0005182896) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001209/2021-2022 | 17/MURD | 05/01/2022 | 04/07/2022 | KISMAT ARA BEGUM | 99.02 | 94.76 | 95.7 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di | SM/09763 | Retrofitting | Sinking of 300 X 200mm Dia Tube Well 82 mtr. Deep by D.R. Rig Method using UPVC Pipe (CD) and UPVC Deep Well Screen (RDS) for piped water supply scheme of EDRAKPUR & its adjoining mouzas at Berhampore Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/000187/2022-2023 | 196/BSD | 28/04/2022 | 28/05/2022 | KISMAT ARA BEGAM | 3.95 | 0 | 0 | 0
10 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di | SM/09763 | Retrofitting | Supply and Delivery for Sinking of 300 X 200mm Dia Tube Well 82 mtr. Deep by D.R. Rig Method using UPVC Pipe (CD) and UPVC Deep Well Screen (RDS) for piped water supply scheme of EDRAKPUR & its adjoining mouzas at Berhampore Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/000188/2022-2023 | 197/BSD | 28/04/2022 | 28/05/2022 | KISMAT ARA BEGAM | 4.65 | 0 | 0 | 0
11 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di | SM/09763 | Retrofitting | Supply of C.I specials to join existing AC pipe with UPVC pipe in connection with FHTC of Edrakpur piped water supply scheme of EDRAKPUR & its adjoining mouzas at Nowda Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000138/2022-2023 | 188/BSD | 28/04/2022 | 28/05/2022 | PM CONSTRUCTION | 3.39 | 0 | 0 | 0
Total | [13 empty] | 144.39 | 108.44 | 75.1