## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Choa ( 315510 ) of Choa under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block of Murshidabad District under Murshidabad Divi | SM/09764 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at CHOA G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000515/2021-2022 | 347/BSD | 27/08/2021 | 26/09/2021 | IMAGIN | 4.16 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Choa ( 315510 ) of Choa under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block of Murshidabad District under Murshidabad Divi | SM/09764 | Retrofitting | Relaying of UPVC pipe line from the house of Akbar Miya to the house of Yasin Sk under command area of Choa Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. | ASSISTANT ENGINEER |  | ORD/001611/2021-2022 | 21/BSD | 20/01/2022 | 04/02/2022 | SWAPAN DAS | 4.81 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Choa ( 315510 ) of Choa under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block of Murshidabad District under Murshidabad Divi | SM/09764 | Retrofitting | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Choa (village code 315510) under Choa Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-B | ASSISTANT ENGINEER |  | ORD/000068/2022-2023 | 173/BSD | 12/04/2022 | 27/04/2022 | M/S SUKESH GHOSH | 4.95 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Choa ( 315510 ) of Choa under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block of Murshidabad District under Murshidabad Divi | SM/09764 | Retrofitting | Laying of 160mm dia UPVC pipeline and road restrostion work for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Choa (village code 315510) under Choa Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/000058/2022-2023 | 163/BSD | 12/04/2022 | 27/04/2022 | SUDIPTA GHOSH | 4.84 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Choa ( 315510 ) of Choa under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block of Murshidabad District under Murshidabad Divi | SM/09764 | Retrofitting | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Choa (village code 315510) under Choa Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/000066/2022-2023 | 171/BSD | 12/04/2022 | 27/04/2022 | BARMAN ENTERPRISE | 4.83 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Choa ( 315510 ) of Choa under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block of Murshidabad District under Murshidabad Divi | SM/09764 | Retrofitting | Laying of 90mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Choa (village code 315510) under Choa Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/000067/2022-2023 | 172/BSD | 12/04/2022 | 27/04/2022 | SOUVIK HALDER | 4.85 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Choa ( 315510 ) of Choa under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block of Murshidabad District under Murshidabad Divi | SM/09764 | Retrofitting | Relaying of UPVC pipeline from the house of Akbar Miya to the house of Yasin SK under command area of choa W/S Scheme under BSD PHE DTE. Tender no - 176 of 21-22 by AE BSD |  |  | VCH/001553/2021-2022 | 448-MSD/21-22 | 31/03/2022 | 31/03/2022 | SWAPAN DAS | 4.81 | 0 | 0 | 0
Total | [13 empty] | 33.25 | 0 | 0