## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh | SM/09767 | Retrofitting | Laying of 125mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Selamatpur (village code 315421) under Selamatpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-B | ASSISTANT ENGINEER |  | ORD/000059/2022-2023 | 164/BSD | 12/04/2022 | 27/04/2022 | M/S SUKESH GHOSH | 4.84 | 4.84 | 100 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh | SM/09767 | Retrofitting | Providing Functional Household Tap Connections (FHTC) of 1329 nos in connection with Jal Swapna (Jal Jeevan Mission ) & Laying of Distribution system of Selamatpur ( Village Code -315421) under Selamatpur Ground Based Piped Water Supply Scheme for Arsenic Affected Areas of Berhampore Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000047/2022-2023 | 1058/MURD | 25/04/2022 | 24/06/2022 | M/S. S. DAS AND ENTERPRISE | 94.54 | 61 | 64.52 | 90
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh | SM/09767 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and Laying of Distribution system of Selamatpur ( village code: 315421 ) of Ground Based piped water supply scheme under Berhampore Sub-Division, Murshidabad Division, PHE Dte. For 35 nos FHTC. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000545/2022-2023 | 156/BSD | 12/04/2022 | 12/05/2022 | ALOK BANERJEE ENTERPRISE | 4.84 | 0 | 0 | 100
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh | SM/09767 | Retrofitting | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Selamatpur (village code 315421) under Selamatpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/000061/2022-2023 | 166/BSD | 12/04/2022 | 27/04/2022 | M/S LOKENATH CONSTRUCTION | 4.83 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh | SM/09767 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (JalJeevan Mission) and Laying of Distribution system of Selamatpur ( village code: 315421 ) Ground Based piped water supply scheme under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. For 35nos FHTC. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000167/2022-2023 | 156/BSD | 12/04/2022 | 12/05/2022 | ALOK BANERJEE ENTERPRISE | 4.84 | 3.27 | 67.48 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh | SM/09767 | Retrofitting | Laying of 125mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Selamatpur (village code 315421) under Selamatpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-A | ASSISTANT ENGINEER |  | ORD/000056/2022-2023 | 161/BSD | 12/04/2022 | 27/04/2022 | SWAPAN DAS | 4.84 | 4.84 | 100 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh | SM/09767 | Retrofitting | Laying of 140mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Selamatpur (village code 315421) under Selamatpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/000062/2022-2023 | 167/BSD | 12/04/2022 | 27/04/2022 | SWAPAN DAS | 4.84 | 4.84 | 100 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh | SM/09767 | Retrofitting | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Selamatpur (village code 315421) under Selamatpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/000060/2022-2023 | 165/BSD | 12/04/2022 | 27/04/2022 | AMIT KUMAR SAHA | 4.85 | 4.85 | 100 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh | SM/09767 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000018/2021-2022 | 539/3/MURD | 25/02/2022 | 25/02/2022 | Resource Division | 7.3 | 0 | 0 | 0
10 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh | SM/09767 | Retrofitting | Laying of 110mm dia upvc ppeline FHTC .......................SELAMATPUR UNDER SELAMATPUR W/S SCHEME. TENDER NO 210 -21-22 |  |  | VCH/000313/2022-2023 | 179-MSD/22-23 | 26/05/2022 | 26/05/2022 | M/S LOKNATH CONSTRUCTION | 4.83 | 0 | 0 | 0
11 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh | SM/09767 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL |  |  | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 15/12/2023 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
12 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh | SM/09767 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL |  |  | BILL/00974/2023-2024 |  | 14/12/2023 | 14/12/2023 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
Total | [13 empty] | 231.27 | 83.65 | 36.17