## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh | SM/09841 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at RAMPUR-I G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000518/2021-2022 | 350/BSD | 27/08/2021 | 26/09/2021 | S.S.INFRASTRUCTURE | 4.16 | 4.16 | 100 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh | SM/09841 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village KANDIBANDHA (Village Code 315327) under SAHAJADPUR Ground Water Based Water Supply Scheme for arsenic affected areas of BERHAMPORE Block in the District of Murshidabad. Tender no - 832 of 20-21 by EE MURD |  |  | VCH/000728/2022-2023 | 256-MSD/22-23 | 12/08/2022 | 12/08/2022 | MAJUMDER CONSTRUCTION | 9.67 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh | SM/09841 | Retrofitting | Continuation Order for Hiring of 01(one) no. Diesel Bolero /Marshal Car for official use having license for contract carriage permit from the Regional Transport Authority for the office of the Assistant Engineer, Murshidabad RWS Sub-Division, for 06(Six) months. (i.e. 01/04/2022 to 30/09/2022) | ASSISTANT ENGINEER (HQ) |  | ORD/001800/2021-2022 | 151/HQ | 25/03/2022 | 31/03/2022 | SISIR KUMAR DE | 0.91 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh | SM/09841 | Retrofitting | Continuation Order for Hiring of one no. Diesel Bolero/Marshal/Ambassador car (WB57B4454) for official use of the Assistant Engineer, Kandi Sub-Division, P. H. Engineering Dte. for 03(Three)Months.(Period from 01.04.2022 to 30.06.2022) | ASSISTANT ENGINEER |  | ORD/001626/2021-2022 | 98/BSD | 22/03/2022 | 25/03/2022 | SISIR KUMAR DE | 0.91 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh | SM/09841 | Retrofitting | Continuation work order for Hiring of one no. Diesel Maxi Cab/ Bolero Car/Marshal/Same category for official use of the Executive Engineer, Murshidabad Division, P.H.Engineering Dte. Berhampore, Murshidabad for the period for 6(Six) Months. (i.e 01.12.2022 to 31.05.2023) | ASSISTANT ENGINEER (HQ) |  | ORD/000619/2022-2023 | 326/HQ | 25/11/2022 | 25/05/2023 | DULAL CHOWDHURY | 0.91 | 1.6 | 176.03 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh | SM/09841 | Retrofitting | HIRING OF CAR OF SE-MC |  |  | VCH/001078/2022-2023 | 435-MSD/22-23 | 10/12/2022 | 10/12/2022 | HASNA BEWA | 1.02 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh | SM/09841 | Retrofitting | HIRING OF CAR EE-MSD, OCT-22 NOV-22 |  |  | VCH/001076/2022-2023 | 434-MSD/22-23 | 08/12/2022 | 08/12/2022 | DULAL CHOWDHURY | 0.78 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh | SM/09841 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL |  |  | BILL/00974/2023-2024 |  | 14/12/2023 | 14/12/2023 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh | SM/09841 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL |  |  | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 15/12/2023 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
10 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh | SM/09841 | Retrofitting | HIRING OF VEHICLE OF AE-JSD...FROM 01/09/2022 TO 26/10/2022 |  |  | VCH/001101/2022-2023 | 444-MSD/22-23 | 15/12/2022 | 15/12/2022 | MADAN MOHAN SASMAL | 0.42 | 0 | 0 | 0
11 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh | SM/09841 | Retrofitting | HIRING OF CAR FOR AE-KSD |  |  | VCH/001248/2022-2023 | 524-MSD/22-23 | 03/02/2023 | 03/02/2023 | SISIR KUMAR DE | 5.4 | 0 | 0 | 0
12 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh | SM/09841 | Retrofitting | HIRING OF CAR FOR AE-JSD, W/O NO- 29/MURD, 06/01/2022 |  |  | VCH/001250/2022-2023 | 526-MSD/22-23 | 11/02/2023 | 11/02/2023 | MADAN MOHAN SASMAL | 0.48 | 0 | 0 | 0
13 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh | SM/09841 | Retrofitting | Continuation Order for Hiring of one no. Diesel Bolero/Marshal/Ambassador car (WB57B4454) for official use of the Assistant Engineer, Kandi Sub-Division, P. H. Engineering Dte. for 06(SIX)Months.(Period from 01.07.2022 to 31.12.2022) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000357/2022-2023 | 264/BSD | 22/06/2022 | 22/12/2022 | SISIR KUMAR DE | 0.91 | 0 | 0 | 100
14 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh | SM/09841 | Retrofitting | Providing Balance Functional Household Tap Connection (FHTC) of 462 left out household in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahammadpur (Village code 315549) under Mahammadpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. |  | JUNIOR ENGINEER 1 | ORD/001810/2021-2022 | 802/MURD | 24/03/2022 | 23/04/2022 | M/S. UNIQUE BUILDERS | 29.37 | 0.01 | 0.05 | 1
Total | [13 empty] | 145.64 | 5.77 | 3.96