## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10010 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (Edrakpur PWSS Scheme, Block - Nowda) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. |  | JUNIOR ENGINEER 1 | ORD/000842/2021-2022 | 3275/MURD | 05/10/2021 | 04/12/2021 | RADIANT | 6.22 | 6.22 | 100 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10010 | Augmentation | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Edrakpur Water Supply Scheme of TW-I at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000583/2022-2023 | 3067/MURD | 17/11/2022 | 17/12/2022 | M/S B.R. SUPPLIERS | 10.6 | 9.98 | 94.12 | 100
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10010 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000184/2023-2024 | 1210/MURD/01 | 02/05/2023 | 02/05/2023 | Resource Division | 11.39 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10010 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Edrakpur ground water based water supply scheme under Block- Nowda, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000087/2023-2024 | 1887/MEDB | 16/06/2023 | 16/09/2023 | SRI KRISHNA NIRMAN | 11.66 | 10.05 | 86.25 | 50
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10010 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000354/2023-2024 | 305/MURD/3 | 29/01/2024 | 29/01/2024 | Resource Division | 9.58 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10010 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000349/2023-2024 | 112/MURD/06 | 11/01/2024 | 11/01/2024 | Resource Division | 26.32 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10010 | Augmentation | NEW CONNECTION EDRAKPU PH-I |  |  | BILL/01625/2023-2024 | 471/WBSEDCL-JJM | 20/03/2024 | 20/03/2024 | WBSEDCL | 20.76 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10010 | Augmentation | Edrakpur & Adjoining Mouzas Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nowda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000014/2023-2024 | 982/MURD | 10/04/2023 | 08/05/2026 | SANJAY BISWAS | 643.42 | 344.07 | 53.48 | 85
9 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10010 | Augmentation | Construction Pump House with chlorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement) and 55 mtr. Boundary wall at 3rd Tubewell site of Gangadhari & Edrakpur Pipe water supply scheme under Berhampore Sub Division within Murshidabad Division . | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000102/2024-2025 | 2152/MURD | 29/07/2024 | 21/11/2025 | PARUL ELECTRICAL INSTALLER | 16.6 | 0 | 0 | 80
10 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10010 | Augmentation | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jagaipur PWSS TW-I,II, Chandpur Zone-I PWSS T.W.-II, Edrakpur PWSS T.W-II, Surangapur Zone-IA TW-I of Nowda Block under Berhampore Sub-Division,Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000498/2024-2025 | 663/MURD | 19/03/2025 | 23/05/2025 | SARKAR WATER SUPPLY AGENCY | 58.87 | 0 | 0 | 0
11 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10010 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 100 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for EDRAKPUR Ground Based Water Supply Scheme in Nawda Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000027/2025-2026 | 1021/MURD | 05/05/2025 | 04/07/2025 | SANJAY BISWAS | 40.44 | 0 | 0 | 0
Total | [13 empty] | 855.85 | 370.32 | 43.27