## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10011 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (MALIBARI PWSS Scheme, Block - Raninagar-II) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000831/2021-2022 | 3264/MURD | 05/10/2021 | 04/12/2021 | RADIANT | 5.89 | 5.89 | 99.98 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10011 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000053/2022-2023 | 3052/F/MURD | 17/11/2022 | 17/11/2022 | Resource Division | 23.33 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10011 | Augmentation | Sinking of 01 (One) No of 250mm x 150 mm dia Repalcement tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Malibari Water Supply Scheme of 3rd TW Site under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER |  | ORD/000581/2022-2023 | 3064/MURD | 17/11/2022 | 17/12/2022 | SUJIT KUMAR SAHA | 9.21 | 8.09 | 87.84 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10011 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-III of Malibari ground water based water supply scheme under Block- Raninagar-II, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000833/2023-2024 | 3774/MEDB | 03/11/2023 | 03/02/2024 | ARINDAM MAJUMDAR | 11.02 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10011 | Augmentation | Formal work order for laying Distribution System (HDPE Pipe) of for AUGMENTATION of Ground Water Based MALIBARI PWSS to Accommadate FHTC at Raninagar- II Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000170/2022-2023 | 1316/MURD | 20/05/2022 | 17/09/2022 | NAYLA CONSTRUCTION | 217.49 | 183.08 | 84.18 | 100
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10011 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2022-2023 | 2507/C/MURD | 31/08/2022 | 31/08/2022 | Resource Division | 9.22 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10011 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000110/2023-2024 | 1167/MURD/3 | 28/04/2023 | 28/04/2023 | Resource Division | 27.6 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10011 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000044/2024-2025 | MURD/2991/03 | 13/11/2024 | 13/11/2024 | Resource Division | 30.01 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10011 | Augmentation | NEW SERVICE CONNECTION AT MALIBARI PHI, ID304238384 |  |  | BILL/01219/2023-2024 | 287/WBSEDCL-JJM | 24/01/2024 | 24/01/2024 | WBSEDCL | 12.87 | 0 | 0 | 0
10 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10011 | Augmentation | Construction of Two nos Pump House cum Chlorine Room with sanitary and Water Supply Arrangement ,Construction of Boundary Wall of 200 m, Construction of RCC approach road (3 Mtr Wide)of 100 mtr length, Laying of Rising Main, Construction of 450 Cum OHR, Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works and Land Development Works for Augmentation of Malibari Water Supply scheme at Raninagar-II Block under Murshidabad Division,PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 5 | ORD/000024/2024-2025 | 1816/MURD | 20/06/2024 | 01/01/2026 | M/S B.M. INDUSTRIES | 282.92 | 0 | 0 | 50
11 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10011 | Augmentation | Balance & Allied Work for Laying Distribution System , FHTC of Malibari Water Supply Scheme in Raninagar-II Block ,under Murshidabad Division , PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 5 | ORD/000055/2024-2025 | 1986/MURD | 08/07/2024 | 06/07/2025 | DAS TRADING CO. | 95.72 | 0 | 0 | 60
12 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10011 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 100 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for MALIBARI Ground Based Water Supply Scheme in Raninagar -II Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000029/2025-2026 | 1024/MURD | 05/05/2025 | 04/07/2025 | M/S. S. DAS AND ENTERPRISE | 40.44 | 0 | 0 | 0
13 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10011 | Augmentation | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Bilchatra (Village Code -314568) under Malibari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184027) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000714/2020-2021 | 581/MURD | 09/02/2021 | 10/04/2021 | ULTRA CONSTRUCTION. | 27.7 | 5.11 | 18.45 | 1
14 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10011 | Augmentation | Formal work order for Functional Household Tap Connections (FHTC) in Bilchatra & Malibari Village ( Village Code -314568 ,314569 ) in connection with Augmentation of Malibari Ground Water Based Water Supply Scheme Raninagar-II Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 5 | ORD/000686/2022-2023 | 163/MURD | 17/01/2023 | 18/03/2023 | KUNDU CONSTRUCTION | 170.31 | 167.79 | 98.52 | 95
Total | [13 empty] | 963.73 | 369.96 | 38.39