## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Gangadhari PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10012 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (GANGADHARI PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. |  | JUNIOR HARIHARPARA BLOCK | ORD/000843/2021-2022 | 3276/MURD | 05/10/2021 | 04/12/2021 | RADIANT | 3.51 | 3.51 | 100 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Gangadhari PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10012 | Augmentation | Formal work order for Augmentation of laying Rising main & Distribution System of GANGADHARI Water Supply Scheme under Berhampore Sub-Division, Murshidabad Division, P.H.Engg Dte. In the District Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3,JUNIOR HARIHARPARA BLOCK | ORD/000172/2022-2023 | 1303/MURD | 20/05/2022 | 17/09/2022 | PRADIP KUMAR DAS | 300.61 | 299.96 | 99.78 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Gangadhari PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10012 | Augmentation | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gangadhari Water Supply Scheme at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000595/2022-2023 | 3069/MURD | 17/11/2022 | 17/12/2022 | A.M. ENTERPRISE | 10.6 | 9.39 | 88.61 | 100
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Gangadhari PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10012 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000386/2023-2024 | MURD/514 | 16/02/2024 | 16/02/2024 | Resource Division | 21.35 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Gangadhari PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10012 | Augmentation | Construction of 200 Cum OHR, Boundary Wall, Pump House for Augmentation of GANGADHARI PWSS in NAWDA Block, Berhampore Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000850/2023-2024 | 825/MURD | 15/03/2024 | 02/10/2025 | SOM CONSTRUCTION AGENCY | 93.75 | 0 | 0 | 25
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Gangadhari PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10012 | Augmentation | Construction Pump House with chlorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement) and 55 mtr. Boundary wall at 3rd Tubewell site of Gangadhari & Edrakpur Pipe water supply scheme under Berhampore Sub Division within Murshidabad Division . | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000102/2024-2025 | 2152/MURD | 29/07/2024 | 21/11/2025 | PARUL ELECTRICAL INSTALLER | 16.6 | 0 | 0 | 80
7 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation Of Ground Water Based Gangadhari PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10012 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Gangadhari ground water based water supply scheme under Block- Nowda, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000571/2024-2025 | 400/MEDB | 12/02/2025 | 12/05/2025 | M/S. T.K. BASU RAY | 12.18 | 0 | 0 | 70
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Gangadhari PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10012 | Augmentation | Retrofitting Providing Functional Household Tap Connections (FHTC) of 1786 nos in connection with (Jal Jeevan Mission ) and under command area of village of Gangadhari ( Village Code -315534) under Gangadhari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block under Murshidabad Division P.H.E Dte. |  | JUNIOR HARIHARPARA BLOCK | ORD/000134/2022-2023 | 1232/MURD | 11/05/2022 | 10/07/2022 | PRADIP KUMAR DAS | 78.92 | 19.76 | 25.04 | 0
Total | [13 empty] | 537.52 | 332.62 | 61.88