## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10014 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (ARAJI MADHUPUR PWSS Scheme, Block - Berhampore) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. |  | JUNIOR ENGINEER 1 | ORD/000836/2021-2022 | 3269/MURD | 05/10/2021 | 04/12/2021 | RADIANT | 3.15 | 3.15 | 100 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10014 | Augmentation | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Arazi Madhupur Water Supply Scheme of TW-I at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE | ORD/000593/2022-2023 | 3066/MURD | 17/11/2022 | 17/12/2022 | NADIA TUBEWELLS | 10.6 | 9.23 | 87.07 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10014 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000185/2023-2024 | 1210/MURD/02 | 02/05/2023 | 02/05/2023 | Resource Division | 4.99 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10014 | Augmentation | Quotaion for Shifting of LT overhead line at Araji Madhupur head work site. |  |  | BILL/01261/2022-2023 | 206/WBSEDCL | 14/03/2023 | 14/03/2023 | WBSEDCL | 0.79 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10014 | Augmentation | Rail Bhoomi Crossing Seva (IR-RBCS) Eastern Railway Howrah Division DEMAND NOTE Application ID: ER-HWH-2023-WL-01 |  |  | BILL/00290/2023-2024 | 157-MSD/2023-24 | 28/06/2023 | 28/06/2023 | EASTERN RAILWAY (HOWRAH DIVISION) | 5.5 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10014 | Augmentation | Allied work of Laying Distribution System, Rising Main, Construction of Boundary wall, Service Road of Arazi Madhupur & adjoining moujas PWSS under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000035/2024-2025 | 1911/MURD | 02/07/2024 | 09/08/2025 | M/S. GHOSH ENTERPRISE (MANAB KR GHOSH) | 79.82 | 9.4 | 11.78 | 65
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10014 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 16/04/2024 | IMAGIN | 97.48 | 2.79 | 2.86 | 80
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10014 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at ARAZI MADHUPUR Water Supply Scheme at 2nd Site site at BERHAMPORE Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE | ORD/000707/2023-2024 | 3809/MURD | 12/12/2023 | 02/01/2024 | NADIA TUBEWELLS | 11.78 | 10.52 | 89.29 | 90
9 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10014 | Augmentation | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Kanthalia Road (KTLR) Station to Karna Subarna (KNSN) (TP NO 151/33 & 151/36) at Karna Subarna Station Gumti mouza & Connecting with existing 140mm dia HDPE distribution main line of Arazi Madhupur Ground Based W/S Scheme , Berhampore Sub Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000821/2023-2024 | 742/MURD | 12/03/2024 | 10/03/2025 | M/S. GHOSH ENTERPRISE (MANAB KR GHOSH) | 34.02 | 7.71 | 22.66 | 80
10 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10014 | Augmentation | NEW CONNECTION AT ARAJI MADHUPUR PH-II |  |  | BILL/00515/2024-2025 |  | 08/07/2024 | 08/07/2024 | WBSEDCL | 5.17 | 0 | 0 | 0
11 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10014 | Augmentation | NEW CONNECTION AT ARAJI MADHUPUR PH-II |  |  | BILL/00522/2024-2025 | 166/WBSEDCL-JJM | 29/07/2024 | 29/07/2024 | WBSEDCL | 5.17 | 0 | 0 | 0
12 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10014 | Augmentation | Formal work order for Augmentation of Arazi Madhupur & its adjoining mouzas Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Berhampore Block within Berhampore Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000604/2022-2023 | 3171/MURD | 30/11/2022 | 01/10/2025 | M/S. GHOSH ENTERPRISE (MANAB KR GHOSH) | 200.36 | 97.75 | 48.79 | 80
13 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10014 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Araji-Madhupur ground water based water supply scheme under Block- Berhampore, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-II,Junior engineer-III | ORD/000162/2023-2024 | 2019/MEDB | 19/06/2023 | 07/09/2025 | SARKAR CONSTRUCTION | 11.08 | 9.73 | 87.77 | 80
14 | MURSHIDABAD |  | Murshidabad Division | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. | SM/10014 | Augmentation | Relaying of pipe line for connection of Gobindapur Junior High School and 29, Gobindapur Junior Basic School under command area of ARAJIMADHUPUR Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. |  | JUNIOR ENGINEER 1 | ORD/000058/2020-2021 | 3176/MURD | 16/12/2020 | 31/12/2020 | DATA ENTERPRISE | 4.58 | 4.55 | 99.39 | 0
Total | [13 empty] | 474.49 | 154.82 | 32.63