## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. | SM/10015 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (NABIPUR PWSS Scheme, Block - Raninagar-II) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000830/2021-2022 | 3263/MURD | 05/10/2021 | 04/12/2021 | RADIANT | 6.45 | 6.43 | 99.78 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. | SM/10015 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000054/2022-2023 | 3052/G/MURD | 17/11/2022 | 17/11/2022 | Resource Division | 23.03 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. | SM/10015 | Augmentation | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BILPACHAKOPRA (Village Code 314584) under NABIPUR Ground Water Based Water Supply Scheme for arsenic affected areas of RANINAGAR-II Block in the District of Murshidabad. Tender no - 54 of 20-21 by EE MURD |  |  | VCH/001501/2021-2022 | 36-MSD/22-23 | 23/04/2022 | 23/04/2022 | NOVELTY CONSTRUCTION | 6.31 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. | SM/10015 | Augmentation | Formal work order for laying Distribution System (HDPE Pipe) of for AUGMENTATION of Ground Water Based NABIPUR PWSS to Accommadate FHTC at Raninagar- II Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/000043/2022-2023 | 1116/MURD | 29/04/2022 | 27/08/2022 | CHAKRABORTY CONSTRUCTION | 317.51 | 74.49 | 23.46 | 1
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. | SM/10015 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2022-2023 | 2507/D/MURD | 31/08/2022 | 31/08/2022 | Resource Division | 11.45 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. | SM/10015 | Augmentation | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of O.H.R. for Augmentation of Ground Water Based Nabipur PWSS under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001719/2021-2022 | 153/ISD | 17/03/2022 | 16/04/2022 | G MITRA & ASSOCIATES | 1.48 | 1.48 | 100 | 100
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. | SM/10015 | Augmentation | Restoration of Road which were damaged during laying of Pipeline under Islampore Sub Division PHE DTE. under Murshidabad Division PHE DTE. Ref Memo No: 488/ISD Dt. 26.09.2024 of the AE/ISD PHE DTE. |  |  | BILL/01230/2024-2025 | 493-MSD/2024-25 | 04/10/2024 | 04/10/2024 | EXECUTIVE ENGINEER , MURSHIDABAD HIGHWAY DIVISION -I, PWD (ROADS) DIRECT. GOV OF W.B | 9.19 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. | SM/10015 | Augmentation | NEW SERVICE CONNECTION AT NABIPUR PH 3, ID304232739 |  |  | BILL/01230/2023-2024 | 302/WBSEDCL-JJM | 05/02/2024 | 05/02/2024 | WBSEDCL | 3.29 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. | SM/10015 | Augmentation | Providing Functional Household Tap Connections (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Nabipur, Bilpachakopra (Village Code -314590,314584) under Nabipur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 3 | ORD/000641/2022-2023 | 3337/MURD | 15/12/2022 | 26/06/2026 | AZAD ENTERPRISE | 58.72 | 0 | 0 | 70
10 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. | SM/10015 | Augmentation | Formal work order for laying Distribution System (HDPE Pipe) of for AUGMENTATION of Ground Water Based NABIPUR PWSS to Accommadate FHTC at Raninagar- II Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000903/2022-2023 | 1116 /MURD | 29/04/2022 | 23/05/2025 | CHAKRABORTY CONSTRUCTION | 317.51 | 118.78 | 37.41 | 80
11 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. | SM/10015 | Augmentation | Construction of One no Pump House cum Chlorine Room with sanitary and Water Supply Arrangement ,Construction of Boundary Wall of 200 m, Laying of Rising Main, Construction of 450 Cum OHR, Land Development Works at Nabipur Water Supply scheme at Raninagar-II Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000112/2024-2025 | 2302/MURD | 12/08/2024 | 19/04/2025 | PRAFULLYA CONSTRUCTION | 207.59 | 0 | 0 | 0
Total | [13 empty] | 962.52 | 201.19 | 20.9