## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raypur (315531), Madhupur (315532) Kanapara (315541) and Sakua (315542) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of No | SM/10036 | Retrofitting | Laying of 140mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raypur (village code 315531) under Surangapur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000064/2022-2023 | 169/BSD | 12/04/2022 | 27/04/2022 | M/S.S.S. ENTERPRISE | 4.84 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raypur (315531), Madhupur (315532) Kanapara (315541) and Sakua (315542) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of No | SM/10036 | Retrofitting | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raypur (village code 315531) under Surangapur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-I | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000065/2022-2023 | 170/BSD | 12/04/2022 | 27/04/2022 | SOUNAK ENTERPRISE | 4.85 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raypur (315531), Madhupur (315532) Kanapara (315541) and Sakua (315542) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of No | SM/10036 | Retrofitting | Laying of 125mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raypur (village code 315531) under Surangapur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-B | ASSISTANT ENGINEER |  | ORD/000057/2022-2023 | 162BSD | 12/04/2022 | 27/04/2022 | A.S. MONDAL ENTERPRISE | 4.84 | 4.84 | 100 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raypur (315531), Madhupur (315532) Kanapara (315541) and Sakua (315542) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of No | SM/10036 | Retrofitting | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raypur (village code 315531) under Surangapur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-II | ASSISTANT ENGINEER |  | ORD/000063/2022-2023 | 168/BSD | 12/04/2022 | 27/04/2022 | SOUVIK HALDER | 4.86 | 4.86 | 100 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raypur (315531), Madhupur (315532) Kanapara (315541) and Sakua (315542) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of No | SM/10036 | Retrofitting | Laying of 125mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raypur (village code 315531) under Surangapur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-A | ASSISTANT ENGINEER |  | ORD/000055/2022-2023 | 160/BSD | 12/04/2022 | 27/04/2022 | BARMAN ENTERPRISE | 4.84 | 4.84 | 100 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raypur (315531), Madhupur (315532) Kanapara (315541) and Sakua (315542) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of No | SM/10036 | Retrofitting | LAYING OF 140MM DIA FHTC ........ RAYPUR UNDER SURANGAPUR W/S SCHEME UNDER MSD PHE DTE. TENDER NO 213 OF 21-22 |  |  | VCH/000317/2022-2023 | 177-MSD/22-23 | 17/05/2022 | 17/05/2022 | M/S SS ENTERPRISE (SUKESH GHOSH) | 4.84 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raypur (315531), Madhupur (315532) Kanapara (315541) and Sakua (315542) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of No | SM/10036 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000001/2022-2023 | 889/A/MURD | 05/04/2022 | 05/04/2022 | Resource Division | 58.9 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raypur (315531), Madhupur (315532) Kanapara (315541) and Sakua (315542) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of No | SM/10036 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) and under command area of village of Raypur, Kanapara, Sakua, Madhupur (Village code 315531, 315541, 315542, 315532) under Surangapur Ground Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0005182885) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 3 | ORD/001339/2021-2022 | 479/MURD | 22/02/2022 | 01/11/2025 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 398.73 | 30.22 | 7.58 | 30
Total | [13 empty] | 486.7 | 44.75 | 9.19