## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District | SM/10459 | Retrofitting | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- C. | ASSISTANT ENGINEER |  | ORD/000236/2022-2023 | 208/LSD | 11/05/2022 | 10/06/2022 | SOUVIK HALDER | 4.86 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District | SM/10459 | Retrofitting | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Fatejanpur Diar (P) (314911) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District of Lalbagh Sub-Division under Murshidabad Division Phe Dte . Part- A. | ASSISTANT ENGINEER |  | ORD/000245/2022-2023 | 217/LSD | 11/05/2022 | 10/06/2022 | SOUVIK HALDER | 4.91 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District | SM/10459 | Retrofitting | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Fatejanpur Diar (P) (314911) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District of Lalbagh Sub-Division under Murshidabad Division Phe Dte . Part- B. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000246/2022-2023 | 218/LSD | 11/05/2022 | 10/06/2022 | SOUNAK ENTERPRISE | 4.98 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District | SM/10459 | Retrofitting | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- G. | ASSISTANT ENGINEER |  | ORD/000273/2022-2023 | 244/LSD | 11/05/2022 | 10/06/2022 | SOUNAK ENTERPRISE | 4.98 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District | SM/10459 | Retrofitting | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- I. | ASSISTANT ENGINEER |  | ORD/000275/2022-2023 | 246/LSD | 11/05/2022 | 10/06/2022 | SOUVIK HALDER | 4.86 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District | SM/10459 | Retrofitting | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- K. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000277/2022-2023 | 248/LSD | 11/05/2022 | 10/06/2022 | SOUNAK ENTERPRISE | 4.75 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District | SM/10459 | Retrofitting | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- A. | ASSISTANT ENGINEER |  | ORD/000234/2022-2023 | 206/LSD | 11/05/2022 | 10/06/2022 | SOUNAK ENTERPRISE | 4.98 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District | SM/10459 | Retrofitting | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- B. | ASSISTANT ENGINEER |  | ORD/000235/2022-2023 | 207/LSD | 11/05/2022 | 10/06/2022 | AMIT KUMAR SAHA | 4.91 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District | SM/10459 | Retrofitting | Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Azimganj link cable Station ( TP NO 179/26 & 179/27) at Cabin Para mouza & Connecting with existing 250 mm dia UPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000442/2020-2021 | 544/MURD | 05/02/2021 | 07/03/2021 | J.S. CONSTRUCTION | 15.55 | 0 | 0 | 0
10 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District | SM/10459 | Retrofitting | Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Dahapara Dham Station ( TP NO 174/24 & 174/22) at Aminabazar Rail Gumit mouza & Connecting with existing 250 mm dia UPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000426/2020-2021 | 543/MURD | 05/02/2021 | 07/03/2021 | M/S. GOUTAM CHAKRABORTY | 33.47 | 0 | 0 | 0
11 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District | SM/10459 | Retrofitting | Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Azimganj link cable Station ( TP NO 179/11 & 179/10) at Bash Bagan mouza & Connecting with existing 300 mm dia UPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000463/2020-2021 | 545/MURD | 05/02/2021 | 07/03/2021 | M/S. S. DAS AND ENTERPRISE | 12.26 | 0 | 0 | 0
12 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District | SM/10459 | Retrofitting | Continuation work order for Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Azimganj link cable Station ( TP NO 179/26 & 179/27) at Cabin Para mouza & Connecting with existing 250 mm dia UPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000889/2022-2023 | 409/MURD | 15/02/2023 | 17/03/2023 | J.S. CONSTRUCTION | 15.55 | 0 | 0 | 0
13 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District | SM/10459 | Retrofitting | Continuation work order for Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Azimganj link cable Station ( TP NO 179/11 & 179/10) at Bash Bagan mouza & Connecting with existing 300 mm dia UPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. _2 | ASSISTANT ENGINEER |  | ORD/000888/2022-2023 | 408/MURD | 15/02/2023 | 17/03/2023 | M/S. S. DAS AND ENTERPRISE | 12.26 | 0 | 0 | 0
14 | MURSHIDABAD |  | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District | SM/10459 | Retrofitting | Continuation work order for Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Azimganj link cable Station ( TP NO 179/11 & 179/10) at Bash Bagan mouza & Connecting with existing 300 mm diaUPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. _1 | ASSISTANT ENGINEER |  | ORD/000887/2022-2023 | 407/MURD | 15/02/2023 | 17/03/2023 | M/S. S. DAS AND ENTERPRISE | 12.26 | 0 | 0 | 0
Total | [13 empty] | 140.57 | 0 | 0