## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10609 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional Household Connection of different existing PWSS (Sagarpara PWSS Scheme,Block- Jalangi)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. |  |  | VCH/000736/2022-2023 | 260-MSD/22-23 | 18/08/2022 | 18/08/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 11.08 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10609 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000032/2022-2023 | 2780/A/MURD | 01/10/2022 | 01/10/2022 | Resource Division | 30.95 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10609 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000313/2023-2024 | 3037/MURD/2 | 27/09/2023 | 27/09/2023 | Resource Division | 111.86 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10609 | Augmentation | Formal Work Order for Augmentation of Sagarpara Part-B Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 1 | ORD/000532/2022-2023 | 2540/MURD | 02/09/2022 | 20/07/2025 | M/S GUHA AND ROY | 333.77 | 0 | 0 | 8
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10609 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sagarpara Part-B Water Supply Scheme of TW-I,II,III at Head Work Site & 2nd Tube Well Site under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte | ASSISTANT ENGINEER | Junior Engineer | ORD/000669/2022-2023 | 3410/MURD | 22/12/2022 | 20/02/2023 | R.K. DRILLING SERVICES | 35.34 | 0 | 0 | 90
6 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10609 | Augmentation | NEW SERVICE CONNECTION ATSAGARPARA PWSS JL NO 10 PLOT NO RS 2294,2295 MURSHIDABAD ID 304240390 |  |  | BILL/01273/2023-2024 | 301/WBSEDCL-JJM | 05/02/2024 | 05/02/2024 | WBSEDCL | 3.68 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10609 | Augmentation | NEW SERVICE CONNECTION AT SAGARPARA PH ID 304244957 |  |  | BILL/01506/2023-2024 | 406/WBSEDCL-JJM | 04/03/2024 | 04/03/2024 | WBSEDCL | 7.89 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10609 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I,II & III of Sagarpara Part-B ground water based water supply scheme under Block- Jalangi, Dist. Murshidabad under MEDB, PHE Dte | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000837/2023-2024 | 3776/MEDB | 03/11/2023 | 01/09/2025 | ORIENTAL ENGINEERING CO. | 34.92 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10609 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SAGAR PARA PART-B Water Supply Scheme and Chandkati Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 3 | ORD/000722/2023-2024 | 3907/MURD | 20/12/2023 | 15/01/2025 | NADIA TUBEWELLS | 18.43 | 0 | 0 | 100
Total | [13 empty] | 587.92 | 0 | 0