## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10610 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000025/2022-2023 | 2507/G/MURD | 31/08/2022 | 31/08/2022 | Resource Division | 26.31 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10610 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000160/2023-2024 | 1180/MURD/08 | 29/04/2023 | 29/04/2023 | Resource Division | 26.31 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10610 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2024-2025 | MURD/2481/10 | 04/09/2024 | 04/09/2024 | Resource Division | 15.32 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10610 | Augmentation | Formal Work Order for Augmentation of Faridpur Zone-I Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jal Swapna in Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000418/2022-2023 | 2085/MURD | 27/07/2022 | 01/06/2025 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 477.83 | 370.09 | 77.45 | 75
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10610 | Augmentation | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Mouza Tikar Bariakalkihara (314642),of Faridpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000116/2022-2023 | 1199/MURD | 10/05/2022 | 24/06/2022 | NADIA TUBEWELLS | 16.6 | 9.31 | 56.1 | 100
Total | [13 empty] | 562.36 | 379.41 | 67.47