## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10612 | Augmentation | Formal Work Order for Augmentation of Jalangi Zone-I Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jal Swapna in Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000343/2022-2023 | 1875/MURD | 15/07/2022 | 22/09/2025 | DOBAY CONSTRUCTION | 250.61 | 80.67 | 32.19 | 40
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10612 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jalangi Zone-I Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER |  | ORD/000584/2022-2023 | 3053/MURD | 17/11/2022 | 01/01/2023 | MAMATA USHA ENTERPRISE | 23.58 | 21.5 | 91.18 | 1
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10612 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2022-2023 | 2780/E/MURD | 01/10/2022 | 01/10/2022 | Resource Division | 13.39 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10612 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000173/2023-2024 | 1180/MURD/16 | 29/04/2023 | 29/04/2023 | Resource Division | 235.38 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10612 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2024-2025 | MURD/2481/01 | 04/09/2024 | 04/09/2024 | Resource Division | 13.39 | 0 | 0 | 0
Total | [13 empty] | 536.36 | 102.17 | 19.05