## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10627 | Augmentation | Preparation of D.P.R (Consultancy work)in connection with the Functional Household Connection of different existing PWSS (Karimpur- Jalangi Zone-I PWSS Scheme,Block-Jalangi)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 370 of 21-22 by EE MSD. |  |  | VCH/000355/2022-2023 | 185-MSD/22-23 | 13/06/2022 |  | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 9.77 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10627 | Augmentation | Preparation of D.P.R (Consultancy work)in connection with the Functional Household Connection of different existing PWSS(Karimpur- Jalangi Zone-III PWSS Scheme,Block-Jalangi)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 372 of 21-22 by EE MSD. |  |  | VCH/000356/2022-2023 | 185-MSD/22-23 | 13/06/2022 |  | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.38 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10627 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional Household Connection of different existing PWSS(Karimpur- Jalangi Zone-II PWSS Scheme,Block-Jalangi)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 371 of 21-22 by EE MSD. |  |  | VCH/000354/2022-2023 | 185-MSD/22-23 | 13/06/2022 |  | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.24 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10627 | Augmentation | Protection of Head work site premises by raising Boundary wall height by R.B.T fencing with Entrance Gate under Karimpur Jalangi (Zone-I) Water Supply Scheme under Islampur Sub Division, under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000217/2021-2022 | 276/ISD | 03/06/2021 | 02/08/2021 | ROBIN ROY | 3.32 | 3.26 | 98.22 | 1
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10627 | Augmentation | Renovation of Pump House No. 1 of Karimpur Jalangi (Zone-I) Water Supply Scheme under Jalangi Block within Islampur Sub Division, under Murshidabad Division, P.H.E. Dte.in the District Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000301/2021-2022 | 382/A/ISD | 26/07/2021 | 24/09/2021 | ROBIN ROY | 2.25 | 2.23 | 99.41 | 1
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10627 | Augmentation | Relaying of distribution pipeline on damaged line from Node Point 24 to 25 under command area of Karimpur Jalangi Zone-I Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000307/2021-2022 | 388/ISD | 26/07/2021 | 25/08/2021 | ROBIN ROY | 4.83 | 4.79 | 99.24 | 1
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10627 | Augmentation | Relaying of distribution pipeline on damaged line from Node Point 21 to 22 under command area of Karimpur Jalangi Zone-I Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000309/2021-2022 | 382/ISD | 26/07/2021 | 25/08/2021 | R.S CONSTRUCTION (PROP- ROBIN ROY) | 4.82 | 4.79 | 99.46 | 1
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10627 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000164/2023-2024 | 1180/MURD/10 | 29/04/2023 |  | Resource Division | 64.63 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10627 | Augmentation | New connection charge for Karimpur-Jalangi W/S Scheme (Part-B) Zone-I, P/H No.-III. |  |  | BILL/00275/2023-2024 | 94/WBSEDCL-JJM | 11/08/2023 |  | WBSEDCL | 0.78 | 0 | 0 | 0
10 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10627 | Augmentation | New connection charge for Karimpur-Jalangi W/S Scheme (Part-B) Zone-I, P/H No.-IV. |  |  | BILL/00274/2023-2024 | 93/WBSEDCL-JJM | 11/08/2023 |  | WBSEDCL | 0.78 | 0 | 0 | 0
11 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10627 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000043/2022-2023 | 2780/L/MURD | 01/10/2022 |  | Resource Division | 18.05 | 0 | 0 | 0
12 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10627 | Augmentation | ADDL SERVICE CONNECTION CHARGES AT KUTUBPUR VILLAGE ,KARIMPUR JALANGI PWSS PART B, Z 1, PH 3 ID860279295 |  |  | BILL/01107/2023-2024 | 214/WBSEDCL-JJM | 02/01/2024 |  | WBSEDCL | 2.93 | 0 | 0 | 0
13 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10627 | Augmentation | ADDL SERVICE CONNECTION CHARGES AT KUTUBPUR VILLAGE ,KARIMPUR JALANGI PWSS PART B, Z 1, PH 3 ID860279295 |  |  | BILL/01107/2023-2024 | 214/WBSEDCL-JJM | 02/01/2024 |  | WBSEDCL | 2.93 | 0 | 0 | 0
14 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10627 | Augmentation | ADDL SERVICE CONNECTION CHARGES AT KUTUBPUR VILLAGE ,KARIMPUR PWSS PART B, Z 1, PH 4.ID 860281600 |  |  | BILL/01108/2023-2024 | 215/WBSEDCL-JJM | 02/01/2024 |  | WBSEDCL | 2.89 | 0 | 0 | 0
15 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10627 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-I under Karimpur-Jalangi (Part-B) ground water based water supply scheme under Block_ Jalangi Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000046/2023-2024 | 3734/MEDB | 03/11/2023 | 01/02/2024 | KAMAKHYA ENTERPRISE | 24.23 | 8.98 | 37.07 | 50
16 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10627 | Augmentation | Balance Work for Laying of Distribution System for Augmentation of Karimpur-Jalangi Zone-I Part-A Piped water supply scheme to accommodate FHTC (Functional House Hold Tap Connection ) under Jalangi Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000740/2023-2024 | 65/MURD | 08/01/2024 | 08/03/2024 | S.S.INFRASTRUCTURE | 134.77 | 49.94 | 37.06 | 10
17 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10627 | Augmentation | Formal Work Order for Augmentation of Karimpur Jalangi Zone-I(Part-B) Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jal Swapna in Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000356/2022-2023 | 1996/MURD | 21/07/2022 | 21/07/2023 | M/S. BIMALENDU BOSE | 267.14 | 148.52 | 55.6 | 81
18 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10627 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2024-2025 | MURD/2481/07 | 04/09/2024 |  | Resource Division | 18.05 | 0 | 0 | 0
Total | [13 empty] | 567.77 | 222.52 | 39.19