## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MOMENPUR to Accommodate FHTC Block Domkal District - Murshidabad. | SM/10629 | Augmentation | Construction of approach road with earth filling at Head Work Site (T/W No. 1) under Momenpur W/s Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/001234/2021-2022 | 604/ISD | 31/12/2021 | 01/03/2022 | MANAB KUMAR GHOSH | 4.49 | 0 | 0 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MOMENPUR to Accommodate FHTC Block Domkal District - Murshidabad. | SM/10629 | Augmentation | Construction of approch road with earth filling at Head Work Site (T/W No. 1) under Momenpur W/s Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/002063/2021-2022 | 40/ISD | 28/01/2022 | 29/03/2022 | MANAB KUMAR GHOSH | 4.49 | 0 | 0 | 1
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MOMENPUR to Accommodate FHTC Block Domkal District - Murshidabad. | SM/10629 | Augmentation | Inter connection with Tubewell and rising main etc. at Head work sites (T/W-1) &(T/W-2) Both & Allied Works Under Momenpur Water Supply scheme under Islampur Sub - Division,Murshidabad Division P.H.E Dte. In the district of Murshidabad |  |  | VCH/000720/2022-2023 | 245-MSD/22-23 | 12/08/2022 | 12/08/2022 | B.G. ENTERPRISE | 3.04 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MOMENPUR to Accommodate FHTC Block Domkal District - Murshidabad. | SM/10629 | Augmentation | Repairing & Renovation of the pump House No-1 & 2 and allied works under Momenpur water Supply scheme ,Block-Domkal,Under Islampur Sub Division,Under Murshidabad Division, P.H.E Dte. In the District of Murshidabad. |  |  | VCH/000715/2022-2023 | 235-MSD/22-23 | 15/08/2022 | 15/08/2022 | SOUVIK HALDER | 3.6 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MOMENPUR to Accommodate FHTC Block Domkal District - Murshidabad. | SM/10629 | Augmentation | Sinking of 01 (One) No of 250mm x 150 mm dia Repalcement tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Momenpur Water Supply Scheme of 2nd TW Site under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER |  | ORD/000580/2022-2023 | 3063/MURD | 17/11/2022 | 17/12/2022 | SUJIT KUMAR SAHA | 9.21 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MOMENPUR to Accommodate FHTC Block Domkal District - Murshidabad. | SM/10629 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000162/2023-2024 | 1180/MURD/09 | 29/04/2023 | 29/04/2023 | Resource Division | 25.98 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MOMENPUR to Accommodate FHTC Block Domkal District - Murshidabad. | SM/10629 | Augmentation | Formal work order Augmentation of MOMENPUR Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 3 | ORD/000655/2022-2023 | 3436/MURD | 23/12/2022 | 23/12/2023 | M/S. ROY TRADING CO. | 408.18 | 0 | 0 | 30
8 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MOMENPUR to Accommodate FHTC Block Domkal District - Murshidabad. | SM/10629 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-II of Momenpur ground water based water supply scheme under Block- Domkal, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000048/2023-2024 | 2319/MEDB | 11/07/2023 | 11/10/2023 | SRI KRISHNA NIRMAN | 11.66 | 0 | 0 | 10
9 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MOMENPUR to Accommodate FHTC Block Domkal District - Murshidabad. | SM/10629 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000031/2024-2025 | MURD/2481/04 | 04/09/2024 | 04/09/2024 | Resource Division | 11.73 | 0 | 0 | 0
10 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MOMENPUR to Accommodate FHTC Block Domkal District - Murshidabad. | SM/10629 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well of Pump House No. I & II of Zone-II under MOMENPUR AND OTHERS PIPED WATER SUPPLY SCHEME, BLOCK- DOMKAL DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000042/2025-2026 | 1142/MEDB | 14/05/2025 | 14/08/2025 | DAS CONSTRUCTION | 22.95 | 0 | 0 | 15
Total | [13 empty] | 505.33 | 0 | 0