## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10630 | Augmentation | Restoration work of Distribution Pipeline by laying of UPVC pipe at different location of Vulnerable Area of command area of Faridpur-II W/S Scheme under Islampur Sub-Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000577/2022-2023 | 277/ISD | 03/06/2022 | 03/07/2022 | SHIBAM ENTERPRISE | 4.8 | 4.75 | 98.99 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10630 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000046/2022-2023 | 3037/C/MURD | 16/11/2022 |  | Resource Division | 107.03 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10630 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000154/2023-2024 | 1180/MURD/03 | 29/04/2023 |  | Resource Division | 107.03 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10630 | Augmentation | New connection charge for Faridpur W/S Scheme, Zone-II, P/H No.-II. |  |  | BILL/00271/2023-2024 | 91/WBSEDCL-JJM | 11/08/2023 |  | WBSEDCL | 0.8 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10630 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000034/2022-2023 | 2780/C/MURD | 01/10/2022 |  | Resource Division | 24.7 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10630 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2022-2023 | 2508/B/MURD | 31/08/2022 |  | Resource Division | 3.41 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10630 | Augmentation | Addl service connection charges ID 860279294 |  |  | BILL/01104/2023-2024 | 213/WBSEDCL-JJM | 02/01/2024 |  | WBSEDCL | 2.8 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10630 | Augmentation | Addl service connection charges ID 860279294 |  |  | BILL/01104/2023-2024 | 213/WBSEDCL-JJM | 02/01/2024 |  | WBSEDCL | 2.8 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10630 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-II , Zone-II of Faridpur, ground water based water supply scheme under Block- Raninagar-II, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II | ORD/000832/2023-2024 | 3773/MEDB | 03/11/2023 | 01/02/2024 | JOY BISHNU ENGINEERING CO. | 11.74 | 3.81 | 32.45 | 20
10 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10630 | Augmentation | Formal work order for Augmentation of Faridpur Zone-II Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 5 | ORD/000535/2022-2023 | 2642/MURD | 19/09/2022 | 19/09/2023 | PRADIP KUMAR DAS | 742.15 | 227.74 | 30.69 | 45
11 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10630 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2024-2025 | MURD/2481/03 | 04/09/2024 |  | Resource Division | 34.04 | 0 | 0 | 0
Total | [13 empty] | 1041.3 | 236.3 | 22.69