## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10631 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional Household Connection of different existing PWSS(Jalangi PWSS Scheme,Block-Jalangi)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. |  |  | VCH/000353/2022-2023 | 183-MSD/22-23 | 13/06/2022 | 13/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 16.77 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10631 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jalangi Zone-III/ Part-B Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000588/2022-2023 | 3057/MURD | 17/11/2022 | 01/01/2023 | NADIA TUBEWELLS | 23.55 | 20.03 | 85.06 | 100
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10631 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2022-2023 | 2507/B/MURD | 31/08/2022 | 31/08/2022 | Resource Division | 74.09 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10631 | Augmentation | New connection charge for Jalangi W/S Scheme (Part-B) Zone-III, P/H No.-III. |  |  | BILL/00272/2023-2024 | 92/WBSEDCL-JJM | 11/08/2023 | 11/08/2023 | WBSEDCL | 0.9 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10631 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II of JALANGI , Zone- III/Part-B ground water based water supply scheme under Block- Jalangi, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000830/2023-2024 | 3771/MEDB | 03/11/2023 | 03/02/2024 | M/S SAMRIDDHI ENTERPRISE | 20.33 | 15.79 | 77.69 | 50
6 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10631 | Augmentation | NEW SERVICE CONNECTION AT JALANGI PWSS Z3 PLOT LR 538 MURSHIDABAD ID 304238698 |  |  | BILL/01272/2023-2024 | 297/WBSEDCL-JJM | 01/02/2024 | 01/02/2024 | WBSEDCL | 9.63 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10631 | Augmentation | ADDL SERVICE CONNECTION CHARGES AT JOYKRISHNAPUR ,JALANGI PWSS, PART B,Z-3,PH3, ID 860279298 |  |  | BILL/01109/2023-2024 | 212/WBSEDCL-JJM | 02/01/2024 | 02/01/2024 | WBSEDCL | 5.14 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10631 | Augmentation | Payment Cost of repairing road from Biswaspara (SH) to Jortala More PWD Road under Jalangi Block in Murshidabad District vide packeage no WB 13-409. |  |  | BILL/00826/2024-2025 | 303-MSD/2024-25 | 29/08/2024 | 29/08/2024 | EXECUTIVE ENGINER WBSRDA MURSHIDABAD DIVISION | 32.83 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10631 | Augmentation | Formal Work Order for Augmentation of Jalangi Zone III Part B Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 1 | ORD/000340/2022-2023 | 1806/MURD | 11/07/2022 | 01/01/2026 | HOQUEDAR ALI | 149.27 | 0 | 0 | 50
Total | [13 empty] | 332.5 | 35.82 | 10.77