## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10632 | Augmentation | New connection charge for Jalangi W/S Scheme (Part-B) Zone-II, P/H No.-III. |  |  | BILL/00270/2023-2024 | 88/WBSEDCL-JJM | 11/08/2023 | 11/08/2023 | WBSEDCL | 1.27 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10632 | Augmentation | New connection charge for Jalangi W/S Scheme (Part-B) Zone-II, P/H No.-IV. |  |  | BILL/00268/2023-2024 | 87/WBSEDCL-JJM | 11/08/2023 | 11/08/2023 | WBSEDCL | 1.35 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10632 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II of JALANGI , Zone- II/Part-B ground water based water supply scheme under Block- Jalangi, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000824/2023-2024 | 3769/MEDB | 03/11/2023 | 03/02/2024 | P. K. ENGINEERING | 22.5 | 0 | 0 | 65
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10632 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2024-2025 | MURD/2481/09 | 04/09/2024 | 04/09/2024 | Resource Division | 14.57 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10632 | Augmentation | ADDL SERVICE CONNECTION CHARGES AT SAHEBRAMPUR BOLAITALA , JALANGI PWSS PART B,Z2,PH2 ID 860281603 |  |  | BILL/01111/2023-2024 | 211/WBSEDCL-JJM | 02/01/2024 | 02/01/2024 | WBSEDCL | 7.15 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10632 | Augmentation | addl service connection charges at sahebrampur palpara jalangi pwss part b,z 2,ph 4 ID 860279296 |  |  | BILL/01105/2023-2024 | 210/WBSEDCL-JJM | 02/01/2024 | 02/01/2024 | WBSEDCL | 8.59 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10632 | Augmentation | Formal Work Order for Augmentation of Jalangi Zone II Part-B Ground Water Based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) within Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000327/2022-2023 | 1691/MURD | 28/06/2022 | 01/07/2025 | KISMAT ARA BEGAM | 131.01 | 0 | 0 | 75
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/B to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10632 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jalangi Zone-II/ Part-B Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER |  | ORD/000586/2022-2023 | 3055/MURD | 17/11/2022 | 01/01/2023 | MAMATA USHA ENTERPRISE | 23.58 | 0 | 0 | 1
Total | [13 empty] | 210.02 | 0 | 0