## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10633 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000057/2022-2023 | 3294/MURD | 12/12/2022 | 12/12/2022 | Resource Division | 21.86 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10633 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2022-2023 | 2780/D/MURD | 01/10/2022 | 01/10/2022 | Resource Division | 21.86 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10633 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000157/2023-2024 | 1180/MURD/6 | 29/04/2023 | 29/04/2023 | Resource Division | 143.36 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10633 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000332/2023-2024 | 3849/MURD/1 | 14/12/2023 | 14/12/2023 | Resource Division | 1.98 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10633 | Augmentation | New connection charge for Jalangi W/S Scheme (Part-A) Zone-II, P/H No.-I. |  |  | BILL/00273/2023-2024 | 90/WBSEDCL-JJM | 11/08/2023 | 11/08/2023 | WBSEDCL | 1.61 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10633 | Augmentation | New connection charge for Jalangi W/S Scheme (Part-A) Zone-II, P/H No.-II. |  |  | BILL/00269/2023-2024 | 89/WBSEDCL-JJM | 11/08/2023 | 11/08/2023 | WBSEDCL | 0.91 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10633 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II of JALANGI , Zone- II/Part-A ground water based water supply scheme under Block- Jalangi, Dist. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000821/2023-2024 | 3768/MEDB | 03/11/2023 | 03/02/2024 | EASTERN INDIA SALES & SERVICE | 22.55 | 16.77 | 74.37 | 60
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10633 | Augmentation | Allied work of OHR & HDPE Pipeline for Augmentation of Jalangi Zone-II Part-A ground water based PWSS to accommodate FHTC in Jalangi Block in the district of Murshidabad under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000761/2023-2024 | 183/MURD | 18/01/2024 | 17/04/2024 | MAMATA USHA ENTERPRISE | 123.49 | 121.21 | 98.15 | 90
9 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10633 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000351/2023-2024 | 305/MURD | 29/01/2024 | 29/01/2024 | Resource Division | 22.47 | 0 | 0 | 0
10 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10633 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000029/2024-2025 | MURD/2481/02 | 04/09/2024 | 04/09/2024 | Resource Division | 24.04 | 0 | 0 | 0
11 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10633 | Augmentation | addl service connection charges at sahebrampur colony ,jalangi pwss part A,,z 2, ph 2, ID 860279299 |  |  | BILL/01106/2023-2024 | 209/WBSEDCL-JJM | 02/01/2024 | 02/01/2024 | WBSEDCL | 3.77 | 0 | 0 | 0
12 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10633 | Augmentation | Addl quotation for sahebrampur jalangi CCC ID860281601 |  |  | BILL/01183/2023-2024 | 247/WBSEDCL-JJM | 15/01/2024 | 15/01/2024 | WBSEDCL | 11.14 | 0 | 0 | 0
13 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10633 | Augmentation | Formal Work Order for Augmentation of Jalangi Zone-II / Part-A Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000467/2022-2023 | 2372/MURD | 16/08/2022 | 31/03/2025 | MAMATA USHA ENTERPRISE | 670.9 | 475.67 | 70.9 | 100
14 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10633 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jalangi Zone-II/ Part-A Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER |  | ORD/000585/2022-2023 | 3054/MURD | 17/11/2022 | 01/01/2023 | MAMATA USHA ENTERPRISE | 23.58 | 18.81 | 79.79 | 1
Total | [13 empty] | 1093.52 | 632.46 | 57.84