## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- IV to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10634 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jalangi Zone-IV Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER |  | ORD/000589/2022-2023 | 3058/MURD | 17/11/2022 | 01/01/2023 | NADIA TUBEWELLS | 23.55 | 0 | 0 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- IV to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10634 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000041/2022-2023 | 2780/J/MURD | 01/10/2022 | 01/10/2022 | Resource Division | 14.2 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- IV to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10634 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2022-2023 | 2507/E/MURD | 31/08/2022 | 31/08/2022 | Resource Division | 12.41 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- IV to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10634 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000166/2023-2024 | 1180/MURD/12 | 29/04/2023 | 29/04/2023 | Resource Division | 11.14 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- IV to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10634 | Augmentation | New connection charge for Jalangi W/S Scheme (Part-B) Zone-IV, P/H No.-I. |  |  | BILL/00277/2023-2024 |  | 04/08/2023 | 04/08/2023 | WBSEDCL | 0.87 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- IV to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10634 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II of JALANGI , Zone- IV ground water based water supply scheme under Block- Jalangi, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000831/2023-2024 | 3772/MEDB | 03/11/2023 | 30/06/2025 | QUAZI NOZRUL ISLAM | 23.34 | 0 | 0 | 60
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- IV to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10634 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000026/2024-2025 | MURD/2482 | 04/09/2024 | 04/09/2024 | Resource Division | 14.2 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- IV to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10634 | Augmentation | new service connection at Arji Muradpur ID304173525 |  |  | BILL/01184/2023-2024 | 246/WBSEDCL-JJM | 15/01/2024 | 15/01/2024 | WBSEDCL | 4.3 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- IV to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10634 | Augmentation | NEW SERVICE CONNECTION AT ZONE 4 MOUZA MURADPUR JL NO 30 PLOT NO LR 748,749 MURSHIDABAD ID 304240386 |  |  | BILL/01274/2023-2024 | 296/WBSEDCL-JJM | 01/02/2024 | 01/02/2024 | WBSEDCL | 12.21 | 0 | 0 | 0
10 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- IV to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10634 | Augmentation | Formal work order for Augmentation of Jalangi Zone-IV Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jal Swapna in Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000339/2022-2023 | 1807/MURD | 11/07/2022 | 30/03/2025 | H.I.ENTERPRISE | 351.37 | 0 | 0 | 95
Total | [13 empty] | 467.6 | 0 | 0