## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10679 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2022-2023 | 2780/F/MURD | 01/10/2022 | 01/10/2022 | Resource Division | 27.07 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10679 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000156/2023-2024 | 1180/MURD/05 | 29/04/2023 | 29/04/2023 | Resource Division | 220.24 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10679 | Augmentation | Formal Work Order for Augmentation of KARIMPUR Jalangi Zone-I( Part A) Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000358/2022-2023 | 2047/MURD | 26/07/2022 | 22/01/2023 | M/S. S. DAS AND ENTERPRISE | 692.97 | 479.45 | 69.19 | 40
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10679 | Augmentation | Balance Work for Laying of Distribution System for Augmentation of Karimpur-Jalangi Zone-I Part-A Piped water supply scheme to accommodate FHTC (Functional House Hold Tap Connection ) under Jalangi Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000740/2023-2024 | 65/MURD | 08/01/2024 | 08/03/2024 | S.S.INFRASTRUCTURE | 134.77 | 14.7 | 10.91 | 10
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10679 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000034/2024-2025 | MURD/2481/06 | 04/09/2024 | 04/09/2024 | Resource Division | 27.07 | 0 | 0 | 0
Total | [13 empty] | 1102.11 | 494.15 | 44.84