## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION & REJUVENATION OF SEKENDARA WATER SUPLY SCHEME OF RAGHUNATHGANJ-II BLOCK OF MUSHIDABAD DISTRICT. | SM/10811 | Augmentation | Construction 400 Cum OHR for Augmentation of Sekendra Ground water based Piped water supply scheme in Raghunathganj -II Block under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000002/2023-2024 | 944/MURD | 05/04/2023 | 04/04/2024 | PRODEEP KUMAR GHOSH | 132.12 | 52.91 | 40.05 | 50
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION & REJUVENATION OF SEKENDARA WATER SUPLY SCHEME OF RAGHUNATHGANJ-II BLOCK OF MUSHIDABAD DISTRICT. | SM/10811 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000372/2023-2024 | 495/MURD/09 | 15/02/2024 | 15/02/2024 | Resource Division | 33.66 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION & REJUVENATION OF SEKENDARA WATER SUPLY SCHEME OF RAGHUNATHGANJ-II BLOCK OF MUSHIDABAD DISTRICT. | SM/10811 | Augmentation | Formal work order for Laying Distribution System ,FHTC, Construction of 1 (one) no Pump House (4.25m x 3.60m with sanitary and Water Supply Arrangement), Construction of 1 (one) no Toilet Block with sanitary and Water Supply Arrangement and 2(two) nos Pump House repairing. Repairing of Existing OHR Part for Augmentation of SEKENDRA PWSS in Raghunathganj-II Block , Jangipur Sub-Division under Murshidabad Division ,PHE. Dte. | ASSISTANT ENGINEER | ASSISTANT ENGINEER,Junior Engineer 3 | ORD/000758/2022-2023 | 445/MURD | 17/02/2023 | 12/06/2025 | NAYLA CONSTRUCTION | 255.21 | 164.88 | 64.6 | 90
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION & REJUVENATION OF SEKENDARA WATER SUPLY SCHEME OF RAGHUNATHGANJ-II BLOCK OF MUSHIDABAD DISTRICT. | SM/10811 | Augmentation | Providing Functional Household Tap Connections ( 200 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Taraf Rasulpur ( Village Code -314679) and Sekendra ( Village Code -314064) under P.T Rasulpur & Sekendra Ground Water Based Water Supply Scheme under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000110/2024-2025 | 2211/MURD | 02/08/2024 | 01/09/2024 | PRAVAT KUMAR GHOSH | 7.3 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION & REJUVENATION OF SEKENDARA WATER SUPLY SCHEME OF RAGHUNATHGANJ-II BLOCK OF MUSHIDABAD DISTRICT. | SM/10811 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION & REJUVENATION OF SEKENDARA WATER SUPLY SCHEME OF RAGHUNATHGANJ-II BLOCK OF MUSHIDABAD DISTRICT. Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000554/2024-2025 | 336/MEDB | 10/02/2025 | 10/05/2025 | DAS ENTERPRISE (CHOA) | 23.19 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION & REJUVENATION OF SEKENDARA WATER SUPLY SCHEME OF RAGHUNATHGANJ-II BLOCK OF MUSHIDABAD DISTRICT. | SM/10811 | Augmentation | Construction of Boundary wall of 60 m length and pumphouse (5.9 m x 4.825 m) at site no 4 at Sekendra Pwss in Raghunathganj-II Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000069/2025-2026 | 1246/MURD | 29/05/2025 | 28/07/2025 | KALACHAND DAS | 19.25 | 0 | 0 | 0
Total | [13 empty] | 470.74 | 217.79 | 46.27