## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-II to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10997 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 2780/G/MURD | 01/10/2022 | 01/10/2022 | Resource Division | 11.59 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-II to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/10997 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000168/2023-2024 | 1180/MURD/14 | 29/04/2023 | 29/04/2023 | Resource Division | 11.83 | 0 | 0 | 0
Total | [13 empty] | 23.42 | 0 | 0