## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-III to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/11008 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000040/2022-2023 | 2780/I/MURD | 01/10/2022 | 01/10/2022 | Resource Division | 7.57 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-III to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/11008 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000165/2023-2024 | 1180/MURD/11 | 29/04/2023 | 29/04/2023 | Resource Division | 8.83 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-III to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/11008 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000183/2023-2024 | 1210/MURD/29 | 02/05/2023 | 02/05/2023 | Resource Division | 10.21 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-III to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/11008 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2024-2025 | MURD/2481/08 | 04/09/2024 | 04/09/2024 | Resource Division | 7.57 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-III to Accommodate FHTC Block Jalangi District - Murshidabad. | SM/11008 | Augmentation | Formal Work Order for Augmentation of Karimpur Jalangi Zone-III Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) under Jal Swapna in Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000344/2022-2023 | 1876/MURD | 15/07/2022 | 07/09/2026 | J.S. CONSTRUCTION | 194.67 | 190.87 | 98.05 | 90
Total | [13 empty] | 228.85 | 190.87 | 83.4