## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF AHIRON BLOCK-SUTI - I | SM/11164 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000104/2023-2024 | 1167/MURD/1 | 28/04/2023 | 28/04/2023 | Resource Division | 68.84 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF AHIRON BLOCK-SUTI - I | SM/11164 | Augmentation | Laying distribution pipe lines with allied works in connection With Augmentation of Ahiron Water Supply Scheme In Suti - I Block Of Murshidabad District under Murshidabad Division,P.H.E Dte | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000688/2022-2023 | 130/MURD | 16/01/2023 | 17/03/2023 | M/S RUBIET HOSSAIN | 94.31 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF AHIRON BLOCK-SUTI - I | SM/11164 | Augmentation | Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works & Repair of Boundary Wall (140m + 50m)=190 m at T/W-I site & T/W-II site and Construction of approach road of 80 m ,3 mtr wide and 150 mm depth with 1:2:4 ordinary cement concrete with 75 mm sand filling and BFS for Augmentation of Ahiron Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte.(Attached as Annexure -I) | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000661/2023-2024 | 3561/MURD | 21/11/2023 | 20/01/2024 | ASHEM ENTERPRISE | 8.58 | 8.54 | 99.5 | 100
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF AHIRON BLOCK-SUTI - I | SM/11164 | Augmentation | AHIRON & adjoining mouzas PWSS to accommodate Rising Main with allied Laying Distribution under Jal Jeevan Mission, Block- SUTI-I of JANGIPUR Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000839/2023-2024 | 822/MURD | 15/03/2024 | 14/05/2024 | S. DUTTA | 6.88 | 6.83 | 99.27 | 100
Total | [13 empty] | 178.61 | 15.37 | 8.6