## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Chak Bhikhari,(314686) of Juginda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District under Murshidabad Division PheDte. | SM/11231 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Juginda (Zone-II) Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Domkal Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000129/2023-2024 | 1766/MURD | 06/07/2023 | 27/07/2023 | NADIA TUBEWELLS | 35.34 | 32.07 | 90.77 | 90
2 | MURSHIDABAD |  | Murshidabad Division | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Chak Bhikhari,(314686) of Juginda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District under Murshidabad Division PheDte. | SM/11231 | Augmentation | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Juginda, Kupila and Narsinghpur Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000109/2022-2023 | 1193/MURD | 10/05/2022 | 29/01/2026 | MAMATA USHA ENTERPRISE | 32.62 | 0 | 0 | 20
3 | MURSHIDABAD |  | Berhampore Mechanical | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Chak Bhikhari,(314686) of Juginda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District under Murshidabad Division PheDte. | SM/11231 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well of Pump House No. I & II of Zone-II under MOMENPUR AND OTHERS PIPED WATER SUPPLY SCHEME, BLOCK- DOMKAL DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000042/2025-2026 | 1142/MEDB | 14/05/2025 | 14/08/2025 | DAS CONSTRUCTION | 22.95 | 0 | 0 | 15
Total | [13 empty] | 90.91 | 32.07 | 35.28