## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MITHIPUR | SM/11457 | Augmentation | Laying Distribution System and Construction of 1 (one) no Toilet Block with sanitary and Water Supply Arrangement & 2(two) nos Pump House Office cum godown repairing., for Augmentation of MITHIPUR PWSS in Raghunathganj-II Block , Jangipur Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000704/2022-2023 | 145/MURD | 17/01/2023 | 17/04/2023 | MONDAL ENTERPRISE | 82.55 | 69.23 | 83.86 | 80
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MITHIPUR | SM/11457 | Augmentation | Construction of 250 Cum OHR for Augmentation of Mithipur Water Supply Scheme in Raghunathganj-II Block , Jangipur Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000722/2022-2023 | 172/MURD | 18/01/2023 | 01/01/2026 | SANJIB GHOSH | 94.37 | 40.77 | 43.21 | 100
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MITHIPUR | SM/11457 | Augmentation | Retrofitting Functional Household Tap Connection (FHTC) under Jal Jeevan Mission for command area of Augmentation MITHIPUR Water Supply Scheme in Raghunathganj-II Block , Jangipur Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000705/2022-2023 | 119/MURD | 13/01/2023 | 12/02/2023 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 49.44 | 49.44 | 99.99 | 100
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MITHIPUR | SM/11457 | Augmentation | Sinking of 01 (One) No of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mithipur Water Supply Scheme as required at Raghunathganj-II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000102/2023-2024 | 1743/MURD | 06/07/2023 | 16/03/2025 | NADIA TUBEWELLS | 11.78 | 0 | 0 | 100
5 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MITHIPUR | SM/11457 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000306/2023-2024 | 1295/MURD/06 | 11/05/2023 | 11/05/2023 | Resource Division | 6.13 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MITHIPUR | SM/11457 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of MITHIPUR ground water based water supply scheme under Block- RAGHUNATHGANJ-II, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000156/2023-2024 | 585/MEDB | 31/01/2024 | 30/04/2024 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 12.8 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MITHIPUR | SM/11457 | Augmentation | Engagement of Consultant for Field Data collection, pipeline network analysis by analyzing actual household demand in pipeline sections, identification of low pressure areas with in the pipe network system and proposing probable solution of the same in 2(Two) nos water supply schemes in Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000071/2024-2025 | 2022/MURD | 11/07/2024 | 21/06/2025 | DHPE | 15.34 | 2.3 | 15 | 25
8 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MITHIPUR | SM/11457 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000025/2024-2025 | MURD/2481 | 04/09/2024 | 04/09/2024 | Resource Division | 23.69 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MITHIPUR | SM/11457 | Augmentation | Installation of flow measuring devices on distribution network of MITHIPUR WATER SUPPLY SCHEME OF JANGIPUR SUB-DIVISION UNDER MURSHIDABAD DIVISION, PHE DTE. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000070/2025-2026 | 1245/MURD | 29/05/2025 | 28/06/2025 | DHPE | 3.21 | 0 | 0 | 0
Total | [13 empty] | 299.31 | 161.74 | 54.04