## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11560 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Godhanpara PWSS Scheme, Block - Raninagar-II) to be Augmentation/ Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000738/2021-2022 | 2744/MURD | 03/09/2021 | 02/11/2021 | RADIANT | 11.27 | 3.76 | 33.33 | 0
2 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11560 | Augmentation | Formal work order for Laying of Distribution system,Rising Main, Sub-soil Investigation and construction of OHR (300 cum) and construction of Boundary wall and repairing of Pump-House in connection wih Augmentation of Godhanpara Zone-III water supply scheme under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 1 | ORD/000543/2022-2023 | 2729/MURD | 27/09/2022 | 01/09/2026 | PRIYANKA CONSTRUCTION | 270.88 | 183.93 | 67.9 | 80
3 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11560 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Godhanpara Zone-III Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000590/2022-2023 | 3059/MURD | 17/11/2022 | 01/01/2023 | GENUINE | 23.5 | 20.83 | 88.66 | 100
4 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11560 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000045/2022-2023 | 3037/D/MURD | 16/11/2022 | 16/11/2022 | Resource Division | 40.31 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11560 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000050/2022-2023 | 3052/C/MURD | 17/11/2022 | 17/11/2022 | Resource Division | 17.71 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11560 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000294/2023-2024 | 1278/MURD/12 | 10/05/2023 | 10/05/2023 | Resource Division | 37.4 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11560 | Augmentation | NEW SERVICE CONNECTION AT GODHANPARA Z3 PH I, ID304232740 |  |  | BILL/01223/2023-2024 | 286/WBSEDCL-JJM | 24/01/2024 | 24/01/2024 | WBSEDCL | 6.75 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11560 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works forAugmentation in connention to Accommodate FHTC at Pump House No.-I, Zone-III under Godhanpara Ground Water Based Piped Water Supply Scheme under Block- Raninagar-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000560/2024-2025 | 342/MEDB | 10/02/2025 | 10/05/2025 | J. S. CONSTRUCTION | 11.36 | 0 | 0 | 90
Total | [13 empty] | 419.19 | 208.52 | 49.74