## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11561 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS ( SAKTIPUR PWSS Scheme, Block - Beldanga-II) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. |  | JUNIOR ENGINEER_RAGHUNATHGANJ - II BLOCK | ORD/000833/2021-2022 | 3266/MURD | 05/10/2021 | 04/12/2021 | RADIANT | 10.43 | 0 | 0 | 0
2 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11561 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Shaktipur Zone-I &II Water Supply Scheme at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. |  | JUNIOR ENGINEER_RAGHUNATHGANJ - II BLOCK | ORD/000598/2022-2023 | 3072/MURD | 17/11/2022 | 01/01/2023 | NADIA TUBEWELLS | 21.18 | 0 | 0 | 1
3 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11561 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000298/2023-2024 | 1278/MURD/3 | 10/05/2023 | 10/05/2023 | Resource Division | 129.08 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11561 | Augmentation | Formal Work Order for Augmentation of Saktipur Zone-I Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Beldanga-II Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000540/2022-2023 | 2860/MURD | 19/10/2022 | 01/04/2025 | M/S. ROY TRADING CO. | 302.59 | 0 | 0 | 80
5 | MURSHIDABAD |  | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11561 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I (H.W Site) at Zone-I and Pump House No.-I (H.W Site) at Zone-II of Saktipur ground water based water supply scheme under Block- Beldanga-II, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000164/2023-2024 | 2020/MEDB | 19/06/2023 | 19/09/2023 | INDTECH ASSOCIATES | 23.14 | 0 | 0 | 8
6 | MURSHIDABAD |  | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11561 | Augmentation | Saktipur Zone-1 Ph-1 Application No-3004554369 |  |  | BILL/01195/2023-2024 | 254/WBSEDCL-JJM | 17/01/2024 | 17/01/2024 | WBSEDCL | 2.98 | 0 | 0 | 0
Total | [13 empty] | 489.4 | 0 | 0