## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION | SM/11568 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (SURANGAPUR PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000841/2021-2022 | 3274/MURD | 05/10/2021 | 04/12/2021 | RADIANT | 15.07 | 0 | 0 | 1
2 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION | SM/11568 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000099/2022-2023 | 702/MURD | 13/03/2023 | 13/03/2023 | Resource Division | 48.15 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION | SM/11568 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000174/2023-2024 | 1180/MURD/17 | 29/04/2023 | 29/04/2023 | Resource Division | 48.15 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION | SM/11568 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Surangapur Zone-II Water Supply Scheme at HW Site & 2nd TW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000743/2022-2023 | 383/MURD | 10/02/2023 | 27/03/2023 | MAMATA USHA ENTERPRISE | 23.58 | 0 | 0 | 100
5 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION | SM/11568 | Augmentation | Hiring of Diesel driven Bolero/ Equivalent four wheeler car for the official use of the Executive Engineer under Office of the Executive Engineer, Mechanical/Electrical Division, PHE Dte. In the District of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000655/2022-2023 | 886/AE-II/MEDB | 12/08/2022 | 11/12/2022 | M/S SAJAHAN CHOWDHURY | 0.59 | 0 | 0 | 10
6 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION | SM/11568 | Augmentation | Hiring of Diesel driven Bolero/Equivalent four wheeler car for the official use of the Assistant Engineer-I under Office of the Executive Engineer, Mechanical/electrical Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000694/2022-2023 | 656/AE/MEDB | 31/03/2023 | 30/09/2023 | M/S SAJAHAN CHOWDHURY | 0.9 | 0 | 0 | 10
7 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION | SM/11568 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I, II & III under SURANGAPUR (ZONE- II ),Part-A ground water based water supply scheme under Block_ Nowda Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000042/2023-2024 | 1881/MEDB | 16/06/2023 | 16/09/2023 | GHOSH BROTHERS | 33.54 | 0 | 0 | 40
8 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION | SM/11568 | Augmentation | Construction of Boundary wall at H/O site, land Development & Approach Road in connection with Augmentation of Surangapur Zone - II PWSS under Murshidabad Division , PHE Dte. Length -266 mtr. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000746/2023-2024 | 82/MURD | 09/01/2024 | 09/03/2024 | BENGAL ENTERPRISE (PROP:-HADIKUL MOLLA) | 29.85 | 0 | 0 | 80
9 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION | SM/11568 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2024-2025 | 1811/MURD/09 | 20/06/2024 | 20/06/2024 | Resource Division | 38.22 | 0 | 0 | 0
10 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION | SM/11568 | Augmentation | NEW CONNECTION SURANGAPUR Z-II PH-II |  |  | BILL/01626/2023-2024 | 483/WBSEDCL-JJM | 21/03/2024 | 21/03/2024 | WBSEDCL | 12.41 | 0 | 0 | 0
11 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION | SM/11568 | Augmentation | Augmentation of Ground Water Based Surangapur Zone - II (PART -A), Salar PWSS Zone-IA, IB, IIA & IIB accommodate 2752 Nos FHTC, Laying Distribution System, Laying Rising Main in Nowda & Bharatpur - II Block within Murshidabad District under Murshidabad Division, PHE Dte.(PART-A) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 | ORD/000543/2023-2024 | 3148/MURD | 09/10/2023 | 26/11/2025 | M/S GUHA & ROY ENTERPRISE | 996.68 | 0 | 0 | 20
12 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION | SM/11568 | Augmentation | Laying of distribution pipe line of 280 mm dia. HDPE pipe line From Node Point J-22 to J-27 ,J-6 to J-822 & J-82 to J-83 and Laying of 150, 250 mm dia ( For casing ) at Surangapur Zone -II PWSS under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000739/2023-2024 | 53/MURD | 05/01/2024 | 04/02/2024 | M/S GUHA AND ROY | 30.62 | 0 | 0 | 100
13 | MURSHIDABAD |  | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION | SM/11568 | Augmentation | Formal Work Order for Augmentation of SURANGAPUR Zone-II (Part -A) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000501/2022-2023 | 2417/MURD | 22/08/2022 | 01/03/2025 | M/S GUHA AND ROY | 343.47 | 0 | 0 | 100
Total | [13 empty] | 1621.23 | 0 | 0