## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11571 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Katlamari PWSS Scheme, Block - Raninagar-II) to be Augmentation / Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000739/2021-2022 | 2745/MURD | 03/09/2021 | 02/11/2021 | RADIANT | 11.14 | 5.57 | 49.99 | 1
2 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11571 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000052/2022-2023 | 3052/E/MURD | 17/11/2022 | 17/11/2022 | Resource Division | 9.64 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11571 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000103/2023-2024 | 1167/MURD | 28/04/2023 | 28/04/2023 | Resource Division | 57.64 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11571 | Augmentation | Formal work order for Laying of Distribution (part-III) and Providing Functional Household Connection to 670 nos household & Construction of Boundary wall of Katlamari Zone -II of Islampur Sub Division under Murshidabad Division,P.H.E Dte.[(i)Amount for LDS & FHTC: Rs.14312870.00 & (ii)Amount for Construction of Boundary wall : Rs.897464.00] | ASSISTANT ENGINEER | Junior Engineer | ORD/000676/2022-2023 | 57/MURD | 06/01/2023 | 07/03/2023 | SOM CONSTRUCTION AGENCY | 132.94 | 0 | 0 | 10
5 | MURSHIDABAD |  | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11571 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,Zone-II under KATLAMARI ground water based water supply scheme under Block_ RANINAGAR-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000887/2023-2024 | 4051/MEDB | 01/12/2023 | 01/03/2024 | M/S K.P. PRAMANIK | 34.44 | 27.94 | 81.11 | 20
6 | MURSHIDABAD |  | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11571 | Augmentation | NEW SERVICE CONNECTION AT KATLAMARI Z2 PH2, ID304232741 |  |  | BILL/01220/2023-2024 | 282/WBSEDCL-JJM | 24/01/2024 | 24/01/2024 | WBSEDCL | 5.04 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11571 | Augmentation | NEW SERVICE CONNECTION AT KATLAMARI Z2 PH 3, ID304232745 |  |  | BILL/01225/2023-2024 | 284/WBSEDCL-JJM | 24/01/2024 | 24/01/2024 | WBSEDCL | 4.37 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11571 | Augmentation | NEW SERVICE CONNECTION AT KATLAMRI Z2 PH I, ID304232748 |  |  | BILL/01222/2023-2024 | 283/WBSEDCL-JJM | 24/01/2024 | 24/01/2024 | WBSEDCL | 3.2 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11571 | Augmentation | Formal work order for Laying of Distribution System (part-II) and Providing Functional Household Tap Connection to 550 nos household & Sub-soil Investigation and Construction of OHR (500 cum) of Katlamari Zone -II of Islampur Sub-Division under Murshidabad Division,P.H.E Dte | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 8 | ORD/000611/2022-2023 | 3244/MURD | 06/12/2022 | 26/12/2025 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 214.83 | 143.72 | 66.9 | 18
10 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11571 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Katlamari Zone-II Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER |  | ORD/000591/2022-2023 | 3060/MURD | 17/11/2022 | 01/01/2023 | GENUINE | 23.5 | 18.95 | 80.65 | 0
11 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11571 | Augmentation | Formal work order Laying of Distribution System (part-I) , Rising Main and Providing Functional Household Tap Connection to 790 nos household & Construction of Pump House of Katlamari Zone -II of Islampur Sub-Division under Murshidabad Division,P.H.E Dte [ (i)Amount for LDS,R. Main & FHTC:: Rs.1,38,47,328.00 & (ii)Amount for Construction of Pump House : Rs.15,28,347.00] | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 8 | ORD/000685/2022-2023 | 162/MURD | 17/01/2023 | 01/02/2026 | SOUNAK ENTERPRISE | 153.68 | 80.12 | 52.13 | 10
12 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11571 | Augmentation | Allied work for Construction of Boundary Wall & Approach Road at Katlamari ZONE-II Ground water based Piped water supply scheme within Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | Junior Engineer,JUNIOR ENGINEER 1,JUNIOR ENGINEER 8 | ORD/000049/2024-2025 | 1948/MURD | 04/07/2024 | 30/05/2025 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 38.57 | 0 | 0 | 80
Total | [13 empty] | 689 | 276.29 | 40.1