## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bahadurpur Piped Water Supply Scheme Block Suti-I District - Murshidabad. | SM/11712 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 04/04/2022 | STEELCONC AND ASSOCIATES | 81.43 | 3.4 | 4.17 | 100
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bahadurpur Piped Water Supply Scheme Block Suti-I District - Murshidabad. | SM/11712 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000096/2023-2024 | 1147/MURD/11 | 27/04/2023 | 27/04/2023 | Resource Division | 19.36 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bahadurpur Piped Water Supply Scheme Block Suti-I District - Murshidabad. | SM/11712 | Augmentation | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 2,Junior Engineer 3,JUNIOR ENGINEER 6 | ORD/000556/2023-2024 | 3218/MURD | 13/10/2023 | 12/10/2024 | BIJAY CHOWDHURY | 2120.16 | 0 | 0 | 5
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Bahadurpur Piped Water Supply Scheme Block Suti-I District - Murshidabad. | SM/11712 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Bahadurpur Piped Water Supply Scheme Block Suti-I District - Murshidabad. under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000548/2024-2025 | 331/MEDB | 10/02/2025 | 10/05/2025 | M/S. T.K. BASU RAY | 21.53 | 0 | 0 | 50
Total | [13 empty] | 2242.47 | 3.4 | 0.15