## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bahadurpur Piped Water Supply Scheme Block Suti-I District - Murshidabad. | SM/11712 | Augmentation | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of DOGACHHI (Village code 313848) under DOGACHHI under Ground Water Based Water Supply Scheme (SAMSERGANJ Block) and BAHADURPUR (Village Code-313924) under BAHADURPUR Ground Water Based Water Supply Scheme for (SUTI-I BLOCK) Arsenic Affected Areas of under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/002129/2021-2022 | 557 /MURD | 28/02/2022 | 27/08/2022 | M/S. NANDY ENTERPRISE | 268.47 | 45.81 | 17.06 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bahadurpur Piped Water Supply Scheme Block Suti-I District - Murshidabad. | SM/11712 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 04/04/2022 | STEELCONC AND ASSOCIATES | 81.43 | 3.4 | 4.17 | 100
3 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bahadurpur Piped Water Supply Scheme Block Suti-I District - Murshidabad. | SM/11712 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000096/2023-2024 | 1147/MURD/11 | 27/04/2023 | 27/04/2023 | Resource Division | 19.36 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Bahadurpur Piped Water Supply Scheme Block Suti-I District - Murshidabad. | SM/11712 | Augmentation | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 2,Junior Engineer 3,JUNIOR ENGINEER 6 | ORD/000556/2023-2024 | 3218/MURD | 13/10/2023 | 12/10/2024 | BIJAY CHOWDHURY | 2120.16 | 0 | 0 | 5
Total | [13 empty] | 2489.42 | 49.21 | 1.98