## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Jotkamal Zone - II Piped Water Supply Scheme Block Raghunathganj- II District - Murshidabad. | SM/11713 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 04/04/2022 | STEELCONC AND ASSOCIATES | 81.43 | 3.26 | 4 | 100
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Jotkamal Zone - II Piped Water Supply Scheme Block Raghunathganj- II District - Murshidabad. | SM/11713 | Augmentation | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jotkomol Zone-II Water Supply Scheme of TW-I HW Site under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000582/2022-2023 | 3065/MURD | 17/11/2022 | 17/12/2022 | M/S B.R. SUPPLIERS | 10.6 | 9.12 | 86.03 | 100
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Jotkamal Zone - II Piped Water Supply Scheme Block Raghunathganj- II District - Murshidabad. | SM/11713 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Jotkamal , Zone-II ground water based water supply scheme under Block- Raghunathganj-II Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000095/2023-2024 | 3784/MEDB | 03/11/2023 | 03/02/2024 | DAS ENTERPRISE (CHOA) | 11.29 | 8.97 | 79.48 | 20
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Jotkamal Zone - II Piped Water Supply Scheme Block Raghunathganj- II District - Murshidabad. | SM/11713 | Augmentation | Allied works for Renovation of Existing IEP (Capacity 54 Cu.M/hr) at Jotkamal Zone-II W/S Scheme in connection with Augmentation of Jotkamal (Zone-II) PWSS under Murshidabad Division P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000834/2023-2024 | 784/MURD | 14/03/2024 | 03/04/2024 | M/S BAPPA ENTERPRISE | 11.26 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Jotkamal Zone - II Piped Water Supply Scheme Block Raghunathganj- II District - Murshidabad. | SM/11713 | Augmentation | Renovation of Existing IEP (Capacity 58 Cu.M/hr) for changing of 01 No Iron Removal Filter media unit of (3.30 m dia x 1.50 M HOS) & 01 No Oxidation Chember of (1.00 M dia x 1.00 M HOS) and painting all vessel, pipes etc. all complete for Augumentation of JOTKOMAL ZONE-II Pipe Water supply scheme, Block-Raghunathganj-II, under Murshidabad Division P.H.E Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000662/2023-2024 | 3560/MURD | 21/11/2023 | 21/12/2023 | M/S BAPPA ENTERPRISE | 4.89 | 3.94 | 80.52 | 100
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Jotkamal Zone - II Piped Water Supply Scheme Block Raghunathganj- II District - Murshidabad. | SM/11713 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SRIKANTABATI PART B & JOTKAMAL ZONE -II Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER,JUNIOR ENGINEER 6 | ORD/000620/2023-2024 | 3395/MURD | 01/11/2023 | 22/11/2023 | KALACHAND DAS | 18.4 | 12.8 | 69.56 | 100
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Jotkamal Zone - II Piped Water Supply Scheme Block Raghunathganj- II District - Murshidabad. | SM/11713 | Augmentation | Sinking of 01 (One) No of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JOTKOMAL ZONE-II Water Supply Scheme as required at Suti-II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 2,JUNIOR ENGINEER 6 | ORD/000630/2023-2024 | 3425/MURD | 02/11/2023 | 23/11/2023 | SUJIT KUMAR SAHA | 11.79 | 8.65 | 73.39 | 100
8 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Jotkamal Zone - II Piped Water Supply Scheme Block Raghunathganj- II District - Murshidabad. | SM/11713 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well of Pump House No. II and NEW OHR SITE of Zone-II under JOTKAMAL PIPED WATER SUPPLY SCHEME, BLOCK- DOMKAL RAGHUNATHGANJ-II DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000021/2025-2026 | 1143/MEDB | 14/05/2025 | 14/08/2025 | HANNAN BUILDERS PVT LTD | 22.73 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Jotkamal Zone - II Piped Water Supply Scheme Block Raghunathganj- II District - Murshidabad. | SM/11713 | Augmentation | Augmentation of Ground Water Based JOT KAMAL (ZONE-I), JOTKAMAL (Zone-II) & JOTKAMAL (Zone-III) PWSS, Block- RAGHUNATHGANJ-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000282/2023-2024 | 2643/MURD | 23/08/2023 | 01/04/2025 | M/S NIRAPADA BHATTACHARJEE | 1194.05 | 107.41 | 9 | 10
Total | [13 empty] | 1366.45 | 154.15 | 11.28