## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/11715 | Augmentation | Formal Work order for Hiring of Maxicab ( Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on Daily hire basis for official use of the Dy Superintending Engineer, Murshidabad Circle,PHE Dte.[Period for 01(One) Year] for the month of April?2022 to March?2023 | ASSISTANT ENGINEER (HQ) |  | ORD/000569/2022-2023 | 894/MURD | 05/04/2022 | 05/04/2023 | SOUMYADIP MISRA | 4.78 | 0 | 0 | 1
2 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/11715 | Augmentation | Formal work order for Construction 250 Cum OHR & Rising Main in Connection with Augmentation of Dogachhi Zone-II Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Samserganj Block of Murshidabad District under Murshidabad Division, PHE.Dte. [ (i)Amount for R. Main: Rs. 6,69,620.00 & (ii) Amount for OHR : Rs. 98,29,869.00] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000696/2022-2023 | 134/MURD | 16/01/2023 | 16/01/2024 | IOTA CONSTRUCTION | 104.46 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/11715 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGUMENTATION in connection to Accommodate FHTC at Pump House No.-I , II and III OF ZONE-II under Dogachhi ground water based water supply scheme under Block_ SAMSERGANJ Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000161/2023-2024 | 2087/MEDB | 19/06/2023 | 19/09/2023 | ORIENTAL ENGINEERING CO. | 31.45 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/11715 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 04/04/2022 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 0 | 100
5 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/11715 | Augmentation | Geotechnical study of underground formation of the proposed Over Head Reservoir of Dogachhi (Zone-II) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000756/2023-2024 | 139/MURD | 16/01/2024 | 15/02/2024 | IOTA CONSTRUCTION | 2.48 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/11715 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Dogachhi Zone -II Water Supply Scheme at Head Work Site, 2nd Site & 3 r d site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,Junior Engineer 3 | ORD/000101/2023-2024 | 1742/MURD | 06/07/2023 | 01/04/2025 | NADIA TUBEWELLS | 35.34 | 0 | 0 | 33
7 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/11715 | Augmentation | Overhauling of 350 Cum Capacity, 20 mtr staging height (Shaft Wall) R.C.C. Elevated Reservoir, Repairing of Pump House & Boundary Wall, Laying of Distribution System to accommodate of FHTC work at Alamsahi village, Balbalpara village, Laskarpur village(80%) & Mahisha Thali Village for Augmentation work of Dogachhi Zone-II Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000045/2024-2025 | 1949/MURD | 04/07/2024 | 03/05/2025 | MOTI INDUSTRIES | 93.51 | 0 | 0 | 40
8 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/11715 | Augmentation | Laying of Distribution System for Augmentation of DOGACHHI (ZONE-II) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000032/2024-2025 | 1891/MURD | 01/07/2024 | 01/07/2025 | TIPU CONSTRUCTION (PROP. SUJAUDDIN ) | 77.48 | 0 | 0 | 40
9 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/11715 | Augmentation | Laying of Rising Main & Distribution System (PART-B) for Augmentation of DOGACHHI (ZONE-II) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000251/2024-2025 | 229/MURD | 27/01/2025 | 27/04/2025 | M/S GUNGUN CONSTRUCTION | 89.6 | 0 | 0 | 0
10 | MURSHIDABAD |  | Murshidabad Division | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. | SM/11715 | Augmentation | Laying of balance work of HDPE pipe Risingmain and construction of approach road at Head Works Site of Dogachhi ( Zone-I) Water Supply Scheme under Jangipur Sub Division,P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000062/2020-2021 | 282/MURD | 27/01/2021 | 26/02/2021 | HARUN ALL RASHID & BROTHERS | 4.96 | 0 | 0 | 1
Total | [13 empty] | 525.48 | 0 | 0