## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11792 | Augmentation | Construction of new Boundary wall with R.B.T fencing with approach road (Pump No-II) under Godhanpara Zone-II Water Supply Scheme under Islampur Sub Division, under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/002061/2021-2022 | 275/ISD. | 03/06/2021 | 02/08/2021 | AJOY GHOSH | 4.52 | 4.52 | 99.94 | 1
2 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11792 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Godhanpara PWSS Scheme, Block - Raninagar-II) to be Augmentation/ Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000738/2021-2022 | 2744/MURD | 03/09/2021 | 02/11/2021 | RADIANT | 11.27 | 0 | 0 | 0.25
3 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11792 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2022-2023 | 3052/B/MURD | 17/11/2022 |  | Resource Division | 18.01 | 0 | 0 | 0
4 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11792 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000293/2023-2024 | 1278/MURD/11 | 10/05/2023 |  | Resource Division | 14.88 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11792 | Augmentation | Shifting of 11KV HTOH line at Godhanpara W/S scheme, P.H-I, Z-II. |  |  | BILL/00262/2023-2024 | 70/WBSEDCL-JJM | 18/07/2023 |  | WBSEDCL | 3.27 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11792 | Augmentation | NEW SERVICE CONNECTION AT GODHANPARA Z2 PH 2, ID304232744 |  |  | BILL/01224/2023-2024 | 281/WBSEDCL-JJM | 24/01/2024 |  | WBSEDCL | 3.68 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. | SM/11792 | Augmentation | Formal work order for Laying of Distribution system, Rising Main, Sub-soil Investigation and construction of OHR (400 cum) and construction of Boundary wall and repairing of Pump-House in connection with Augmentation of Godhanpara Zone-II water supply scheme under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000579/2022-2023 | 3032/MURD | 16/11/2022 | 16/11/2023 | M/S GUHA & ROY ENTERPRISE | 412.1 | 198.25 | 48.11 | 50
Total | [13 empty] | 467.73 | 202.77 | 43.35