## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. | SM/12985 | Support-WQMSP | Maintenance & Servicing of Computer & its accessories and Laboratories maintenance (Sweeping & Cleaning)of 9 numbers sub district water testing laboratories under Murshidabad Division. P.H. Engineering Dte. 4,C.R.Das Road Berhampore, Murshidabad. for 12(Twelve) months (Period from 03-11-2021 to 02-11-2022) | ASSISTANT ENGINEER (HQ) |  | ORD/001199/2021-2022 | 270/HQ | 03/11/2021 | 15/11/2021 | A.S. COMPUTER | 4.84 | 4.84 | 100 | 0
2 | MURSHIDABAD |  | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. | SM/12985 | Support-WQMSP | Chemical, glassware & instrumments requirment for NABL accreditation at Murshidabad District Water Testing Laboratory as per ISO/IEC: 17025: 2017 under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER (HQ) |  | ORD/001127/2021-2022 | 2728/MURD | 03/09/2021 | 13/09/2021 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 14.36 | 1.49 | 10.37 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. | SM/12985 | Support-WQMSP | Supplying and Delivery of laboratory Chemicals/reagents to 19(Nineteen) nos. Water Testing Laboratory for National Rural Drinking Water Quality Testing Monitoring & Surveillance programme in State of West Bengal under Murshidabad Division, P.H.E.Dte. ( For Six months) | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/001589/2021-2022 | 340/MURD | 10/02/2022 | 25/02/2022 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 2.9 | 2.9 | 100 | 0
4 | MURSHIDABAD |  | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. | SM/12985 | Support-WQMSP | Supplying and Delivery of laboratory Chemicals/reagents & Glassware to 19(Nineteen) nos. Water Testing Laboratory for National Rural Drinking Water Quality Testing Monitoring & Surveillance programme in State of West Bengal under Murshidabad Division, P.H.E.Dte. ( For Six months) | ASSISTANT ENGINEER (HQ) |  | ORD/001622/2021-2022 | 443/MURD | 18/02/2022 | 05/03/2022 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 3.89 | 3.88 | 99.7 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. | SM/12985 | Support-WQMSP | Maintenance & servicing of Computer and Computer accessories of 10 nos Old Water Testing Laboratories(Sub District Laboratories -03 nos. NGO Managed Laboratories- 06 and District Water Testing Laboratories) and supply of 10 nos UPS 600 VA under the Office of the Executive Engineer , Murshidabad Division , P.H. Engineering Dte. 4, C.R.Das Road Berhampore, Murshidabad. for. 12(Twelve) months . |  |  | VCH/000945/2022-2023 | 367-MSD/22-23 | 21/10/2022 | 21/10/2022 | ARINDAM MAJUMDAR | 1.44 | 0 | 0 | 0
6 | MURSHIDABAD |  | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. | SM/12985 | Support-WQMSP | ASDFA |  |  | VCH/000998/2022-2023 |  | 04/11/2022 | 04/11/2022 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 2.9 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. | SM/12985 | Support-WQMSP | PROVIDE THE ELECTRICFICATION OF SALAR SUB DISTRICT LAB, TNO- 10/2022-23/AEHQ |  |  | VCH/000952/2022-2023 | 383-MSD/22-23 | 23/10/2022 | 23/10/2022 | ARINDAM MAJUMDAR | 2.35 | 0 | 0 | 0
8 | MURSHIDABAD |  | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. | SM/12985 | Support-WQMSP | SUPPLYING & DELIVERY OF LAB EQUIPMENTS FOR WT LAB INCLUDING DELIVERY OF CHEMICALS OF SURFACE WATER SUPPLY OF JIAGANJ AZIMGANJ & ITS ADJ MOUJAS. |  |  | VCH/000946/2022-2023 | 368-MSD/22-23 | 21/10/2022 | 21/10/2022 | A.S. COMPUTER | 1.86 | 0 | 0 | 0
9 | MURSHIDABAD |  | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. | SM/12985 | Support-WQMSP | Supplying and Delivery of laboratory Chemicals/reagents and Glassware to Murshidabad District Water Testing Laboratory for AAS Operation under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER (HQ) |  | ORD/000754/2020-2021 | 2536/MURD | 30/09/2020 | 31/10/2020 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.17 | 2.45 | 58.83 | 10
10 | MURSHIDABAD |  | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. | SM/12985 | Support-WQMSP | Supply & delivery of Reagents & Consumables for On-Site Mobile Analysis System for Murshidabad district of West Bengal as per scope and direction of EIC under Public Health Engineering Department, Government of West Bengal. | ASSISTANT ENGINEER (HQ) |  | ORD/001602/2021-2022 | 80/HQ | 15/02/2022 | 17/03/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT LTD. | 4.98 | 4.98 | 100 | 0
11 | MURSHIDABAD |  | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. | SM/12985 | Support-WQMSP | CARRYING REFERRAL WATER SAMPLES TO STATE LABORATORY. |  |  | BILL/00417/2023-2024 | 259-MSD/2023-24 | 19/09/2023 | 19/09/2023 | M/S. DIPTI ENTERPRISE | 0.07 | 0 | 0 | 0
12 | MURSHIDABAD |  | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. | SM/12985 | Support-WQMSP | Repairing & Renovation work of Jangipur Sub District Laboratory building under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000788/2022-2023 | 562/MURD | 28/02/2023 | 20/03/2023 | SARKAR BROTHERS | 5.62 | 5.53 | 98.39 | 0
13 | MURSHIDABAD |  | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. | SM/12985 | Support-WQMSP | Supplying and Delivery of laboratory Chemicals/reagents & Glassware to 19(Nineteen) nos. Water Testing Laboratory for National Rural Drinking Water Quality Testing Monitoring & Surveillance programme in State of West Bengal under Murshidabad Division, P.H.E.Dte. ( For Six months) | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000684/2022-2023 | 113/MURD | 13/01/2023 | 02/02/2023 | M/S LAXMI ENTERPRISE | 14.84 | 14.84 | 100 | 100
14 | MURSHIDABAD |  | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. | SM/12985 | Support-WQMSP | Supplying and Delivery of laboratory Chemicals/reagents to 19(Nineteen) nos. Water Testing Laboratory for National Rural Drinking Water Quality Testing Monitoring & Surveillance programme in State of West Bengal under Murshidabad Division, P.H.E.Dte. ( For Six months) | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000682/2022-2023 | 112/MURD | 13/01/2023 | 02/02/2023 | M/S LAXMI ENTERPRISE | 10.84 | 10.84 | 100 | 100
15 | MURSHIDABAD |  | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. | SM/12985 | Support-WQMSP | Supply & delivery of water quality parameter testing Chemicals, Reagents, Consumables & Glassware for 19 (Nineteen) laboratories for the period of 6 months under Murshidabad Division, PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000792/2023-2024 | 440/MURD | 08/02/2024 | 09/03/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 46.07 | 46.07 | 100 | 100
16 | MURSHIDABAD |  | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. | SM/12985 | Support-WQMSP | Carrying WTP water sample to Kalyani State Referral Laboratory for Pesticide testing and analysis through GCMS |  |  | BILL/01047/2023-2024 | 500-MSD/2023-24 | 17/01/2024 | 17/01/2024 | M/S. DIPTI ENTERPRISE | 0.02 | 0 | 0 | 0
17 | MURSHIDABAD |  | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. | SM/12985 | Support-WQMSP | Carrying referral water samples to state laboratory |  |  | BILL/01046/2023-2024 | 506-MSD/2023-24 | 21/01/2024 | 21/01/2024 | M/S. DIPTI ENTERPRISE | 0.06 | 0 | 0 | 0
18 | MURSHIDABAD |  | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. | SM/12985 | Support-WQMSP | Continuation work order for Sample collection form different AIRP & CPP at different Blocks in the District of Murshidabad under Murshidabad Division, P.H.Engineering Dte. for the period of 01-11-2022 to 30-10-2023 | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000646/2022-2023 | 2904/MURD | 28/10/2022 | 28/10/2023 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 2.36 | 2.17 | 91.75 | 92
19 | MURSHIDABAD |  | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. | SM/12985 | Support-WQMSP | Supplying and Delivery of laboratory Chemicals/reagents & Glassware to 19(Nineteen) nos. Water Testing Laboratory for National Rural Drinking Water Quality Testing Monitoring & Surveillance programme in State of West Bengal under Murshidabad Division, P.H.E.Dte. ( For Six months) | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000683/2022-2023 | 115/MURD | 13/01/2023 | 02/02/2023 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 3.36 | 3.36 | 100 | 100
20 | MURSHIDABAD |  | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. | SM/12985 | Support-WQMSP | Supplying and Delivery of laboratory Chemicals/reagents to 19(Nineteen) nos. Water Testing Laboratory for National Rural Drinking Water Quality Testing Monitoring & Surveillance programme in State of West Bengal under Murshidabad Division, P.H.E.Dte. ( For Six months) | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000680/2022-2023 | 111/MURD | 13/01/2023 | 02/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 28.05 | 28.05 | 100 | 100
21 | MURSHIDABAD |  | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. | SM/12985 | Support-WQMSP | Supplying and Delivery of laboratory Chemicals/reagents & Glassware to 19(Nineteen) nos. Water Testing Laboratory for National Rural Drinking Water Quality Testing Monitoring & Surveillance programme in State of West Bengal under Murshidabad Division, P.H.E.Dte. ( For Six months) | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000681/2022-2023 | 114/MURD | 13/01/2023 | 02/02/2023 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.06 | 10.06 | 100 | 100
22 | MURSHIDABAD |  | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. | SM/12985 | Support-WQMSP | Supply & delivery of water quality parameter testing Chemicals, Reagents, Consumables & Glassware for 19 (Nineteen) laboratories for the period of 6 months under Murshidabad Division, PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 2 | ORD/000791/2023-2024 | 430/MURD | 07/02/2024 | 08/03/2024 | M/S LAXMI ENTERPRISE | 27.17 | 7.19 | 26.48 | 100
Total | [13 empty] | 192.22 | 148.65 | 77.33