## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Murshidabad Division | Detailed Project Report for Augmentation of Jorgachha Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/13486 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER |  | ORD/001469/2021-2022 | 284/MURD | 03/02/2022 | 04/04/2022 | MERCHANDISE-INDIA | 105.32 | 4.68 | 4.44 | 1
2 | MURSHIDABAD |  | Berhampore Mechanical | Detailed Project Report for Augmentation of Jorgachha Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/13486 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II under Jorgachha ground water based water supply scheme under Block_ Domkal Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000044/2023-2024 | 3737/MEDB | 03/11/2023 | 03/05/2024 | JAGANNATH ENTERPRISE | 22.14 | 0 | 0 | 0
3 | MURSHIDABAD |  | Murshidabad Division | Detailed Project Report for Augmentation of Jorgachha Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/13486 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000305/2023-2024 | 1278/MURD/14 | 10/05/2023 | 10/05/2023 | Resource Division | 74.66 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | Detailed Project Report for Augmentation of Jorgachha Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/13486 | Augmentation | JORGACHA PH-III |  |  | BILL/01525/2023-2024 | 434/WBSEDCL-JJM | 12/03/2024 | 12/03/2024 | WBSEDCL | 8.45 | 0 | 0 | 0
5 | MURSHIDABAD |  | Murshidabad Division | Detailed Project Report for Augmentation of Jorgachha Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/13486 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jorgacha Water Supply Scheme at Head Work Site, 2nd Site site at DOMKAL Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000131/2023-2024 | 1757/MURD | 06/07/2023 | 27/07/2023 | R.K. DRILLING SERVICES | 23.58 | 8.77 | 37.2 | 50
6 | MURSHIDABAD |  | Murshidabad Division | Detailed Project Report for Augmentation of Jorgachha Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/13486 | Augmentation | Construction of Boundwary Wall , Pump House , PCC approach road , Land Development for Augmentation of Jorgacha PWSS in Domkol Block , Islampur Sub-Division under Murshidabad Division ,PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3,JUNIOR ENGINEER_BELDANGA 2 BLOCK | ORD/000011/2025-2026 | 899/MURD | 23/04/2025 | 22/07/2025 | EMCO CONSTRUCTION | 23 | 0 | 0 | 0
7 | MURSHIDABAD |  | Murshidabad Division | Detailed Project Report for Augmentation of Jorgachha Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. | SM/13486 | Augmentation | Formal work order for the work of Augmentation of JORGACHA Piped Water Supply Scheme under Jal Jevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3,JUNIOR ENGINEER_DOMKAL BLOCK | ORD/000732/2022-2023 | 365/MURD | 09/02/2023 | 23/08/2025 | ULTRA CONSTRUCTION. | 272.97 | 153.1 | 56.09 | 100
Total | [13 empty] | 530.11 | 166.55 | 31.42