## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | KANDARA AND ADJOINING MOUJAS PWSS | SM/13487 | New | Material Requisition To Resource Division |  |  | RTOR000032/2023-2024 | 1043/MURD/2 | 17/04/2023 | 17/04/2023 | Resource Division | 38.45 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | KANDARA AND ADJOINING MOUJAS PWSS | SM/13487 | New | New connection charge for Kandara, PWSS, P/H No.- I. |  |  | BILL/00857/2023-2024 | 119/WBSEDCL-JJM | 27/09/2023 | 27/09/2023 | WBSEDCL | 4.04 | 0 | 0 | 0
3 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | KANDARA AND ADJOINING MOUJAS PWSS | SM/13487 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under KANDARA ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000038/2023-2024 | 1877/MEDB | 16/06/2023 | 16/09/2023 | M/S SAJAHAN CHOWDHURY | 35.2 | 0 | 0 | 7
4 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | KANDARA AND ADJOINING MOUJAS PWSS | SM/13487 | New | Kandara PH-II Application No- 3004409912 |  |  | BILL/01190/2023-2024 | 250/WBSEDCL-JJM | 16/01/2024 | 16/01/2024 | WBSEDCL | 7.12 | 0 | 0 | 0
5 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | KANDARA AND ADJOINING MOUJAS PWSS | SM/13487 | New | Kandra PH-III Application No- 3004547697 |  |  | BILL/01189/2023-2024 | 249/WBSEDCL-JJM | 16/01/2024 | 16/01/2024 | WBSEDCL | 3.98 | 0 | 0 | 0
6 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | KANDARA AND ADJOINING MOUJAS PWSS | SM/13487 | New | Kandara PH-1 Application no-3004409936 |  |  | BILL/01191/2023-2024 |  | 11/01/2024 | 11/01/2024 | WBSEDCL | 4.04 | 0 | 0 | 0
7 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | KANDARA AND ADJOINING MOUJAS PWSS | SM/13487 | New | Formal work order for the work of KANDARA & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte.( Scheme ID -PH222362286S000) | ASSISTANT ENGINEER | JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000695/2022-2023 | 89/MURD | 10/01/2023 | 10/01/2024 | MAHAVIR PUMPS MANUFACTRURING PVT. LTD. | 649.94 | 0 | 0 | 18
8 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | KANDARA AND ADJOINING MOUJAS PWSS | SM/13487 | New | Laying of Distribution Pipeline and Land Development work at Kandra PWSS of Bharatpur-II Block, Kandi Sub-Division under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000007/2025-2026 | 889/MURD | 22/04/2025 | 06/06/2025 | PAL CONSTRUCTION (SUBHAM PAL) | 12.06 | 0 | 0 | 0
Total | [13 empty] | 754.84 | 0 | 0