## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Kandi | Berhampore Mechanical | UDAYCHANDPUR AND ADJOINING MOUJAS PWSS | SM/13488 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under UDAYCHANDPUR ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte | ASSISTANT ENGINEER-II | Junior engineer-I | ORD/000047/2023-2024 | 1882/MEDB | 16/06/2023 | 16/09/2023 | MENAKA ENTERPRISE | 24.41 | 0 | 0 | 0
2 | MURSHIDABAD | Kandi | Murshidabad Division | UDAYCHANDPUR AND ADJOINING MOUJAS PWSS | SM/13488 | New | Material Requisition To Resource Division |  |  | RTOR000020/2023-2024 | 1210/MURD/40 | 02/05/2023 | 02/05/2023 | Resource Division | 26.76 | 0 | 0 | 0
3 | MURSHIDABAD | Kandi | Murshidabad Division | UDAYCHANDPUR AND ADJOINING MOUJAS PWSS | SM/13488 | New | Formal work order for Construction of 300 Cum OHR, Laying Distribution System (PART-A), Rising Main, FHTC, for Uncovered of UDAY CHANDPUR PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000859/2022-2023 | 793/MURD | 21/03/2023 | 20/03/2024 | M/S. SINHA & SONS | 363.73 | 0 | 0 | 10
4 | MURSHIDABAD | Kandi | Murshidabad Division | UDAYCHANDPUR AND ADJOINING MOUJAS PWSS | SM/13488 | New | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at UDAY CHANDPUR PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte.. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER 2 | ORD/000662/2022-2023 | 3407/MURD | 22/12/2022 | 05/02/2023 | MAMATA USHA ENTERPRISE | 16.82 | 0 | 0 | 80
5 | MURSHIDABAD | Kandi | Berhampore Mechanical | UDAYCHANDPUR AND ADJOINING MOUJAS PWSS | SM/13488 | New | NEW CONNECTION AT UDAYCHANDPUR PH-I |  |  | BILL/01621/2023-2024 | 461/WBSEDCL-JJM | 18/03/2024 | 18/03/2024 | WBSEDCL | 5.84 | 0 | 0 | 0
6 | MURSHIDABAD | Kandi | Murshidabad Division | UDAYCHANDPUR AND ADJOINING MOUJAS PWSS | SM/13488 | New | Formal work order for Construction of Boundwary Wall, Pump House & Laying Distribution System(PART-B) Uncovered of UDAY CHANDPUR PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000734/2022-2023 | 385/MURD | 10/02/2023 | 01/10/2025 | MARUTI CONSTRUCTION AND CO. | 158.53 | 0 | 0 | 35
7 | MURSHIDABAD | Kandi | Murshidabad Division | UDAYCHANDPUR AND ADJOINING MOUJAS PWSS | SM/13488 | New | Laying of UPVC pipeline from Head Work Site to Node point 16, laying of parallel line for FHTC work and Construction of approach road of UDAYCHANDPUR & Adjoining Mouzas Water Supply Scheme of Kandi Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000056/2024-2025 | 1987/MURD | 08/07/2024 | 01/10/2025 | MARUTI CONSTRUCTION AND CO. | 76.01 | 0 | 0 | 40
Total | [13 empty] | 672.1 | 0 | 0