## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | SALINDA AND ADJOINING MOUJAS PWSS | SM/13620 | New | Material Requisition To Resource Division |  |  | RTOR000017/2023-2024 | 1210/MURD/41 | 02/05/2023 | 02/05/2023 | Resource Division | 46.94 | 0 | 0 | 0
2 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | SALINDA AND ADJOINING MOUJAS PWSS | SM/13620 | New | New connection charge for Salinda PWSS, P/H No.-II. |  |  | BILL/00856/2023-2024 | 120/WBSEDCL-JJM | 27/09/2023 | 27/09/2023 | WBSEDCL | 4.94 | 0 | 0 | 0
3 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | SALINDA AND ADJOINING MOUJAS PWSS | SM/13620 | New | Formal Work Order For Laying of Distribution System (Part-B) and Construction of Pump House for Augmentation of SALINDA PWSS of Kandi Sub-Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad | ASSISTANT ENGINEER,ASSISTANT ENGINEER (HQ) | JUNIOR ENGINEER 5 | ORD/000701/2022-2023 | 160/MURD | 16/01/2023 | 01/10/2025 | SOM CONSTRUCTION AGENCY | 146.49 | 87.47 | 59.71 | 39
4 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | SALINDA AND ADJOINING MOUJAS PWSS | SM/13620 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SALINDA ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III | ORD/000036/2023-2024 | 1880/MEDB | 16/06/2023 | 16/09/2023 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 24.14 | 19.48 | 80.69 | 11
5 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | SALINDA AND ADJOINING MOUJAS PWSS | SM/13620 | New | Additional & Balance Work Laying of Distribution System , Land Devolapement of SALINDA PWSS in Bharatpur-II Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000733/2023-2024 | 54/MURD | 05/01/2024 | 04/02/2024 | DHIRENDRANATH MONDAL | 17.25 | 13.15 | 76.19 | 80
6 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | SALINDA AND ADJOINING MOUJAS PWSS | SM/13620 | New | Construction of Pump House Cum Chlorine Room, Boundary Wall, Approach Road & Land Development of Salinda PWSS in Bhratpur-II Block , KANDI Sub-Division under Murshidabad Division , PHE. Dte. |  | JUNIOR ENGINEER 1,JUNIOR ENGINEER 5 | ORD/000848/2023-2024 | 823/MURD | 15/03/2024 | 14/05/2024 | M/S RELIABLE | 27.67 | 0 | 0 | 0
7 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | SALINDA AND ADJOINING MOUJAS PWSS | SM/13620 | New | Sinking of 02(Two) Nos 250 mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SALINDA PWSS at Head Work Site & 2nd Tube Well Site in Bharatpur-II Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000667/2022-2023 | 3406/MURD | 22/12/2022 | 05/02/2023 | INDRAJIT MAZUMDAR | 16.8 | 14.32 | 85.21 | 100
8 | MURSHIDABAD | Bharatpur-II | Berhampore Mechanical | SALINDA AND ADJOINING MOUJAS PWSS | SM/13620 | New | Salinda PH-1 Application no- 3004547659 |  |  | BILL/01188/2023-2024 | 248/WBSEDCL-JJM | 16/01/2024 | 16/01/2024 | WBSEDCL | 3.52 | 0 | 0 | 0
9 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | SALINDA AND ADJOINING MOUJAS PWSS | SM/13620 | New | Formal work order for Construction of 350 Cum OHR,Laying Distribution System (PART-C),Rising Main Connection, FHTC , for Uncovered of SALINDA PWSS in Bharatpur-II Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000729/2022-2023 | 340/MURD | 08/02/2023 | 01/09/2026 | DHIRENDRANATH MONDAL | 387.6 | 365.84 | 94.38 | 25
10 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | SALINDA AND ADJOINING MOUJAS PWSS | SM/13620 | New | Formal Work Order For Laying of Distribution System (Part-A) and Construction of Boundary wall of SALINDA PWSS of Kandi Sub-Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000699/2022-2023 | 161/MURD | 17/01/2023 | 26/08/2025 | TANUSHREE ENTERPRISE | 145.06 | 97.7 | 67.35 | 35
11 | MURSHIDABAD | Bharatpur-II | Murshidabad Division | SALINDA AND ADJOINING MOUJAS PWSS | SM/13620 | New | Allied & Balance Work for Laying of Distribution System, Approach Service Road, Construction of Box Culvert and Land Development of SALINDA PWSS in Bharatpur-I Block, of Kandi Sub-Division under Murshidabad Division ,PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 5 | ORD/000180/2024-2025 | 3143/MURD | 03/12/2024 | 03/03/2025 | DHIRENDRANATH MONDAL | 38.56 | 0 | 0 | 30
Total | [13 empty] | 858.97 | 597.94 | 69.61