## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Burwan | Murshidabad Division | SINGADDA AND ADJOINING MOUJAS PWSS | SM/13722 | New | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 1004/MURD/18 | 17/04/2023 | 17/04/2023 | Resource Division | 24.48 | 0 | 0 | 0
2 | MURSHIDABAD | Burwan | Berhampore Mechanical | SINGADDA AND ADJOINING MOUJAS PWSS | SM/13722 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SINGADDA ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000067/2023-2024 | 1897/MEDB | 16/06/2023 | 01/08/2025 | ABHISEK ENGINEERING CONCERN | 22.61 | 0 | 0 | 30
3 | MURSHIDABAD | Burwan | Berhampore Mechanical | SINGADDA AND ADJOINING MOUJAS PWSS | SM/13722 | New | NEW SERVICE CONNECTION PH 2 SINGADDA PWSS ID 304256291 |  |  | BILL/01450/2023-2024 | 343/WBSEDCL-JJM | 12/02/2024 | 12/02/2024 | WBSEDCL | 4.78 | 0 | 0 | 0
4 | MURSHIDABAD | Burwan | Berhampore Mechanical | SINGADDA AND ADJOINING MOUJAS PWSS | SM/13722 | New | NEW SERVICE CONNECTION PH 1 SINGADDA PWSS ID 30425678 |  |  | BILL/01449/2023-2024 | 342/WBSEDCL-JJM | 12/02/2024 | 12/02/2024 | WBSEDCL | 5.13 | 0 | 0 | 0
Total | [13 empty] | 57.01 | 0 | 0